## Detail3 (hidden)
Details for Sum of LT Carryover Percentage - Week Starting On: LCW 4/6 - 4/20
Week Starting On | Planned story points | Actual delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio
LCW 4/6 - 4/20 | 52 | 36 | 18 | 34 | 2 | 0 | 5 | 11 | 16 | 0.11111 | 0 | 0.27778 | 0.32353 | 0.69231

## Consumer Web Kanban
[8 empty] | Week Starting On | Planned story points | Actual delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio
[8 empty] | 2025: LCW 07/01 - 07/31 | 136 | 136 | 46 | 90 | 0 | 0 | 0 | 0 | 46 | [5 empty] | Row Labels | Sum of V2 | Sum of LT | Row Labels | Sum of Rework | Sum of QA Passed |  | Green
PROJECT HEALTH DASHBOARD | [7 empty] | 2025: LCW 08/01 - 08/31 | 146 | 146 | 36 | 110 | 0 | 0 | 0 | 0 | 36 | [5 empty] | 2025: LCW 12/01- 12/31 | 20 | 103 | 2025: LCW 12/01- 12/31 | 0 | 20 |  | Red
[8 empty] | 2025: LCW 09/01 - 09/30 | 126 | 126 | 25 | 101 | 0 | 0 | 0 | 0 | 25 | [5 empty] | 2026: LCW 01/01 - 01/31 | 24 | 114 | 2026: LCW 01/01 - 01/31 | 0 | 24 |  | Amber
[8 empty] | 2025: LCW 10/01 -10/31 | 124 | 124 | 34 | 90 | 0 | 0 | 0 | 0 | 34 | [5 empty] | 2026: LCW 02/01 - 02/28 | 22 | 113 | 2026: LCW 02/01 - 02/28 | 0 | 22
[8 empty] | 2025: LCW 11/01 - 11/30 | 132 | 132 | 28 | 104 | 0 | 0 | 0 | 0 | 28 | [5 empty] | 2026: LCW 03/01 - 03/31 | 17 | 93 | 2026: LCW 03/01 - 03/31 | 3 | 17
| Project Name | LendingTree |  |  |  | Status Date | 2026-06-02 | 2025: LCW 12/01- 12/31 | 123 | 123 | 20 | 103 | 0 | 0 | 0 | 0 | 20 | [5 empty] | 2026: LCW 04/01 - 04/30 | 29 | 116 | 2026: LCW 04/01 - 04/30 | 0 | 29
| Sub Project | Consumer Web | [5 empty] | 2026: LCW 01/01 - 01/31 | 138 | 138 | 24 | 114 | 0 | 0 | 0 | 0 | 24 | [5 empty] | 2026: LCW 05/01 - 05/31 | 23 | 108 | 2026: LCW 05/01 - 05/31 | 0 | 23
| Delivery Manager | Rajesh |  |  |  | Overall Status | Green | 2026: LCW 02/01 - 02/28 | 135 | 135 | 22 | 113 | 0 | 0 | 0 | 0 | 22 | [5 empty] | Grand Total | 135 | 647 | Grand Total | 3 | 135
| Project Manager/Lead | Amul | [5 empty] | 2026: LCW 03/01 - 03/31 | 110 | 110 | 17 | 93 | 3 | 0 | 0 | 0 | 17
| Client POC | Robert Ploeger | [5 empty] | 2026: LCW 04/01 - 04/30 | 145 | 145 | 29 | 116 | 0 | 0 | 0 | 0 | 29
| Client Feedback | - | [5 empty] | 2026: LCW 05/01 - 05/31 | 131 | 131 | 23 | 108 | 0 | 0 | 0 | 0 | 23 | [5 empty] | Sprint | V2 | LT
Team Allocation
| Off-shore team | Allocated | 1 | Billable | 1
| On-site team | Allocated | 6 | [22 empty] | QA Passed
Rework
[23 empty] | Row Labels | Sum of LT Reopen Percentage | Sum of V2 Reopen Percentage |  | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[23 empty] | 2025: LCW 12/01- 12/31 | 0 | 0 |  | 2025: LCW 12/01- 12/31 | 0 | 0
[23 empty] | 2026: LCW 01/01 - 01/31 | 0 | 0 |  | 2026: LCW 01/01 - 01/31 | 0 | 0
[23 empty] | 2026: LCW 02/01 - 02/28 | 0 | 0 |  | 2026: LCW 02/01 - 02/28 | 0 | 0
[23 empty] | 2026: LCW 03/01 - 03/31 | 0 | 0.17647 |  | 2026: LCW 03/01 - 03/31 | 0 | 0
[23 empty] | 2026: LCW 04/01 - 04/30 | 0 | 0 |  | 2026: LCW 04/01 - 04/30 | 0 | 0
[23 empty] | 2026: LCW 05/01 - 05/31 | 0 | 0 |  | 2026: LCW 05/01 - 05/31 | 0 | 0
[23 empty] | Grand Total | 0 | 0.17647 |  | Grand Total | 0 | 0
[23 empty] | Sprint | V2 | LT | Sprint | V2 | LT
[26 empty] | Row Labels | Sum of Planned Vs Completed ratio
[26 empty] | 2025: LCW 12/01- 12/31 | 1
[26 empty] | 2026: LCW 01/01 - 01/31 | 1
[26 empty] | 2026: LCW 02/01 - 02/28 | 1
[26 empty] | 2026: LCW 03/01 - 03/31 | 1
[26 empty] | 2026: LCW 04/01 - 04/30 | 1
[26 empty] | 2026: LCW 05/01 - 05/31 | 1
[26 empty] | Grand Total | 6
[26 empty] | Sprint | Planned Vs Completed ratio
[23 empty] | Sprint | V2 | LT
[23 empty] | 2025: LCW 12/01- 12/31 | 0 | 0
[23 empty] | 2026: LCW 01/01 - 01/31 | 0 | 0
[23 empty] | 2026: LCW 02/01 - 02/28 | 0 | 0
[23 empty] | 2026: LCW 03/01 - 03/31 | 3 | 0
[23 empty] | 2026: LCW 04/01 - 04/30 | 0 | 0
[23 empty] | 2026: LCW 05/01 - 05/31 | 0 | 0
Note on S1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Assigned.
Note on T1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered by V2.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered by LT.
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story points re-opened by external QA for V2 resources.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story Points Reopen by LT.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Carryover by LT.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total QA Passed by V2

## Detail4 (hidden)
Details for Sum of LT - Week Starting On: 2024: OFF 2/20 - 3/5
Week Starting On | Planned Story Points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed
2024: OFF 2/20 - 3/5 | 40 | 13 | 2 | 11 | 0 | 2 | 10 | 17 | 2

## Detail5 (hidden)
Details for Sum of Planned Vs Completed ratio - Week Starting On: 2025: PHX 01/1 - 01/31
Week Starting On | Planned Story Points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio
2025: PHX 01/1 - 01/31 | 43 | 43 | 11 | 32 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 1

## SEOD
[8 empty] | Week Starting On | Planned story points | Actual delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio
[8 empty] | SEOD 10/07 - 10/21 | 45 |  | 7 | 38 | 0 | 8 | 0 | 8 | [6 empty] | Row Labels | Sum of V2 | Sum of LT | Row Labels | Sum of Rework | Sum of QA Passed |  | Green
PROJECT HEALTH DASHBOARD | [7 empty] | SEOD 10/21 - 11/04 | 46 |  | 11 | 35 | 0 | 2 | 0 | 0 | [6 empty] | SEOD 03/10 - 03/24 | 4 | 22 | SEOD 03/10 - 03/24 | 0 | 4 |  | Red
[8 empty] | SEOD 11/04 - 11/18 | 35 |  | 11 | 24 | 0 | 7 | 0 | 8 | [6 empty] | SEOD 03/24 - 04/07 | 17 | 14 | SEOD 03/24 - 04/07 | 0 | 17 |  | Amber
[8 empty] | SEOD 11/18 - 12/02 | 44 |  | 8 | 36 | 0 | 6 | 0 | 0 | [6 empty] | SEOD 04/07 - 04/21 | 8 | 28 | SEOD 04/07 - 04/21 | 0 | 8
[8 empty] | SEOD 12/02 - 12/16 | 39 |  | 8 | 31 | 0 | 0 | 3 | 10 | [6 empty] | SEOD 04/21 - 05/05 | 16 | 29 | SEOD 04/21 - 05/05 | 0 | 16
| Project Name | LendingTree |  |  |  | Status Date | 2026-06-01 | SEOD 12/16 - 12/30 | 38 |  | 9 | 29 | 0 | 0 | 0 | 13 | [6 empty] | SEOD 05/05 - 05/19 | 11 | 29 | SEOD 05/05 - 05/19 | 0 | 11
| Sub Project | SEOD | [5 empty] | SEOD 12/30 - 01/13 | 44 |  | 10 | 34 | 2 | 5 | 0 | 5 | [6 empty] | SEOD 05/19 - 05/31 | 6 | 18 | SEOD 05/19 - 05/31 | 0 | 6
| Delivery Manager | Rajesh |  |  |  | Overall Status | Green | SEOD 01/13 - 01/27 | 37 |  | 11 | 26 | 0 | 6 | 0 | 6 | [6 empty] | Grand Total | 62 | 140 | Grand Total | 0 | 62
| Project Manager/Lead | Himanshu | [5 empty] | SEOD 01/27 - 02/10 | 47 |  | 8 | 39 | 0 | 5 | 0 | 8
| Client POC | Robert Ploeger | [5 empty] | SEOD 02/10 - 02/24 | 43 |  | 10 | 33 | 0 | 5 | 0 | 9
| Client Feedback | - | [5 empty] | SEOD 02/24 - 03/10 | 44 |  | 11 | 33 | 0 | 7 | 0 | 0 | [6 empty] | Sprint | V2 | LT
| Team Allocation | [6 empty] | SEOD 03/10 - 03/24 | 26 |  | 4 | 22 | 0 | 4 | 0 | 2
| Off-shore team | Allocated | 1 | Billable | 1 |  |  | SEOD 03/24 - 04/07 | 31 |  | 17 | 14 | 0 | 0 | 0 | 0
| On-site team | Allocated | 7(5D + 2QA) |  |  |  |  | SEOD 04/07 - 04/21 | 36 |  | 8 | 28 | 0 | 7 | 0 | 6 | [9 empty] | QA Passed
[8 empty] | SEOD 04/21 - 05/05 | 45 |  | 16 | 29 | 0 | 10 | 0 | 0 | [9 empty] | Rework
[8 empty] | SEOD 05/05 - 05/19 | 40 |  | 11 | 29 | 0 | 11 | 0 | 16
[8 empty] | SEOD 05/19 - 05/31 | 24 |  | 6 | 18 | 0 | 0 | 0 | 0
[23 empty] | Row Labels | Sum of LT Reopen Percentage | Sum of V2 Reopen Percentage |  | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[23 empty] | SEOD 03/10 - 03/24 | 0.18182 | 0 |  | SEOD 03/10 - 03/24 | 0 | 0.090909
[23 empty] | SEOD 03/24 - 04/07 | 0 | 0 |  | SEOD 03/24 - 04/07 | 0 | 0
[23 empty] | SEOD 04/07 - 04/21 | 0.25 | 0 |  | SEOD 04/07 - 04/21 | 0 | 0.21429
[23 empty] | SEOD 04/21 - 05/05 | 0.34483 | 0 |  | SEOD 04/21 - 05/05 | 0 | 0
[23 empty] | SEOD 05/05 - 05/19 | 0.37931 | 0 |  | SEOD 05/05 - 05/19 | 0 | 0.55172
[23 empty] | SEOD 05/19 - 05/31 | 0 | 0 |  | SEOD 05/19 - 05/31 | 0 | 0
[23 empty] | Grand Total | 1.156 | 0 |  | Grand Total | 0 | 0.85692
[23 empty] | Sprint | V2 | LT | Sprint | V2 | LT
[26 empty] | Row Labels | Sum of Planned Vs Completed ratio
[26 empty] | SEOD 03/10 - 03/24 | 0.92308
[23 empty] | Sprint | V2 | LT | SEOD 03/24 - 04/07 | 1
[23 empty] | SEOD 03/10 - 03/24 | 0 | 4 | SEOD 04/07 - 04/21 | 0.83333
[23 empty] | SEOD 03/24 - 04/07 | 0 | 0 | SEOD 04/21 - 05/05 | 1
[23 empty] | SEOD 04/07 - 04/21 | 0 | 7 | SEOD 05/05 - 05/19 | 0.6
[23 empty] | SEOD 04/21 - 05/05 | 0 | 10 | SEOD 05/19 - 05/31 | 1
[23 empty] | SEOD 05/05 - 05/19 | 0 | 11 | Grand Total | 5.3564
[23 empty] | SEOD 05/19 - 05/31 | 0 | 0
[26 empty] | Sprint | Planned Vs Completed ratio
[23 empty] | Sprint | V2 | LT
[23 empty] | SEOD 03/10 - 03/24 | 4 | 22
[23 empty] | SEOD 03/24 - 04/07 | 17 | 14
[23 empty] | SEOD 04/07 - 04/21 | 8 | 28
[23 empty] | SEOD 04/21 - 05/05 | 16 | 29
[23 empty] | SEOD 05/05 - 05/19 | 11 | 29
[23 empty] | SEOD 05/19 - 05/31 | 6 | 18
[23 empty] | Sprint | V2 | LT
[23 empty] | SEOD 03/10 - 03/24 | 0 | 2
[23 empty] | SEOD 03/24 - 04/07 | 0 | 0
[23 empty] | SEOD 04/07 - 04/21 | 0 | 6
[23 empty] | SEOD 04/21 - 05/05 | 0 | 0
[23 empty] | SEOD 05/05 - 05/19 | 0 | 16
[23 empty] | SEOD 05/19 - 05/31 | 0 | 0
Note on S1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Assigned.
Note on T1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered by V2.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered by LT.
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story points re-opened by external QA for V2 resources.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story Points Reopen by LT.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Carryover by LT.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total QA Passed by V2
Note on AF11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ticket is reopened from PD, There is some changes in other template which is not mentioned in AC Reply: One of the ticket is carry over its related to VP Project and there are multiple changes in single ticket and its a very big ticket. There is no training on VP project. It's my first VP ticket so need to understand the code and also write a test case for each component.
Note on AF13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ticket is reopened by reporter accidently during the PD of the ticket

## WPM Scrum
[8 empty] | Week Starting On | Planned story points | Actual delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio
[8 empty] | WPM 09/25 - 10/09 | 39 | 32 | 10 | 22 | 2 | 9 | 0 | 7 | 10 | [5 empty] | Row Labels | Sum of V2 | Sum of LT | Row Labels | Sum of Rework | Sum of QA Passed |  | Green
PROJECT HEALTH DASHBOARD | [7 empty] | WPM 10/09 - 10/23 | 30 | 22 | 2 | 20 | 0 | 5 | 3 | 5 | 2 | [5 empty] | WPM 02/26 - 03/12 | 6 | 35 | WPM 02/26 - 03/12 | 1 | 6 |  | Red
[8 empty] | WPM 10/23 - 11/06 | 42 | 28 | 7 | 21 | 0 | 5 | 0 | 14 | 7 | [5 empty] | WPM 03/12 - 03/26 | 15 | 43 | WPM 03/12 - 03/26 | 0 | 15 |  | Amber
[8 empty] | WPM 11/06 - 11/20 | 36 | 33 | 5 | 28 | 2 | 13 | 0 | 3 | 5 | [5 empty] | WPM 03/26 - 04/09 | 8 | 21 | WPM 03/26 - 04/09 | 0 | 8
[8 empty] | WPM 11/20 - 12/04 | 29 | 21 | 5 | 16 | 0 | 5 | 0 | 8 | 5 | [5 empty] | WPM 04/09 - 04/23 | 2 | 18 | WPM 04/09 - 04/23 | 0 | 2
| Project Name | LendingTree |  |  |  | Status Date | 2026-06-01 | WPM 12/04 - 12/18 | 51 | 28 | 3 | 21 | 0 | 2 | 3 | 20 | 3 | [5 empty] | WPM 04/23 - 05/07 | 15 | 26 | WPM 04/23 - 05/07 | 0 | 15
| Sub Project | WordPress Modernization (WPM) | [5 empty] | WPM 12/18 - 01/15 | 53 | 40 | 9 | 31 | 0 | 5 | 0 | 13 | 9 | [5 empty] | WPM 05/07 - 05/21 | 9 | 22 | WPM 05/07 - 05/21 | 0 | 9
| Delivery Manager | Rajesh |  |  |  | Overall Status | Green | WPM 01/15 - 01/29 | 45 | 37 | 5 | 32 | 0 | 0 | 0 | 8 | 5 | [5 empty] | Grand Total | 55 | 165 | Grand Total | 1 | 55
| Project Manager/Lead | Dayanand | [5 empty] | WPM 01/29 - 02/12 | 46 | 28 | 7 | 21 | 0 | 8 | 0 | 18 | 7
| Client POC | Robert Ploeger | [5 empty] | WPM 02/12 - 02/26 | 46 | 25 | 6 | 19 | 0 | 0 | 0 | 21 | 6
| Client Feedback | - | [5 empty] | WPM 02/26 - 03/12 | 58 | 41 | 6 | 35 | 1 | 9 | 0 | 17 | 6 | [5 empty] | Sprint | V2 | LT
| Team Allocation | [6 empty] | WPM 03/12 - 03/26 | 58 | 58 | 15 | 43 | 0 | 8 | 0 | 0 | 15
| Off-shore team | Allocated | 2+4 | Billable | 2 |  |  | WPM 03/26 - 04/09 | 40 | 29 | 8 | 21 | 0 | 8 | 0 | 11 | 8
| On-site team | Allocated | 4 |  |  |  |  | WPM 04/09 - 04/23 | 34 | 20 | 2 | 18 | 0 | 9 | 3 | 11 | 2 | [8 empty] | QA Passed
[8 empty] | WPM 04/23 - 05/07 | 41 | 41 | 15 | 26 | 0 | 0 | 0 | 0 | 15 | [8 empty] | Rework
[8 empty] | WPM 05/07 - 05/21 | 34 | 31 | 9 | 22 | 0 | 0 | 0 | 3 | 9
[23 empty] | Row Labels | Sum of LT Reopen Percentage | Sum of V2 Reopen Percentage |  | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[23 empty] | WPM 02/26 - 03/12 | 0.25714 | 0.16667 |  | WPM 02/26 - 03/12 | 0 | 0.48571
[23 empty] | WPM 03/12 - 03/26 | 0.18605 | 0 |  | WPM 03/12 - 03/26 | 0 | 0
[23 empty] | WPM 03/26 - 04/09 | 0.38095 | 0 |  | WPM 03/26 - 04/09 | 0 | 0.52381
[23 empty] | WPM 04/09 - 04/23 | 0.5 | 0 |  | WPM 04/09 - 04/23 | 1.5 | 0.61111
[23 empty] | WPM 04/23 - 05/07 | 0 | 0 |  | WPM 04/23 - 05/07 | 0 | 0
[23 empty] | WPM 05/07 - 05/21 | 0 | 0 |  | WPM 05/07 - 05/21 | 0 | 0.13636
[23 empty] | Grand Total | 1.3241 | 0.16667 |  | Grand Total | 1.5 | 1.757
[23 empty] | Sprint | V2 | LT | Sprint | V2 | LT
[26 empty] | Row Labels | Sum of Planned Vs Completed ratio
[26 empty] | WPM 02/26 - 03/12 | 0.7069
[26 empty] | WPM 03/12 - 03/26 | 1
[23 empty] | Sprint | V2 | LT | WPM 03/26 - 04/09 | 0.725
[23 empty] | WPM 02/26 - 03/12 | 6 | 35 | WPM 04/09 - 04/23 | 0.58824
[23 empty] | WPM 03/12 - 03/26 | 15 | 43 | WPM 04/23 - 05/07 | 1
[23 empty] | WPM 03/26 - 04/09 | 8 | 21 | WPM 05/07 - 05/21 | 0.91176
[23 empty] | WPM 04/09 - 04/23 | 2 | 18 | Grand Total | 4.9319
[23 empty] | WPM 04/23 - 05/07 | 15 | 26
[23 empty] | WPM 05/07 - 05/21 | 9 | 22
[26 empty] | Sprint | Planned Vs Completed ratio
[23 empty] | Sprint | V2 | LT
[23 empty] | WPM 02/26 - 03/12 | 1 | 9
[23 empty] | WPM 03/12 - 03/26 | 0 | 8
[23 empty] | WPM 03/26 - 04/09 | 0 | 8
[23 empty] | WPM 04/09 - 04/23 | 0 | 9
[23 empty] | WPM 04/23 - 05/07 | 0 | 0
[23 empty] | WPM 05/07 - 05/21 | 0 | 0
[23 empty] | Sprint | V2 | LT
[23 empty] | WPM 02/26 - 03/12 | 0 | 17
[23 empty] | WPM 03/12 - 03/26 | 0 | 0
[23 empty] | WPM 03/26 - 04/09 | 0 | 11
[23 empty] | WPM 04/09 - 04/23 | 3 | 11
[23 empty] | WPM 04/23 - 05/07 | 0 | 0
[23 empty] | WPM 05/07 - 05/21 | 0 | 3
Note on T1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered by V2.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered by LT.
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story points re-opened by external QA for V2 resources.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story Points Reopen by LT.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Carryover by LT.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total QA Passed by V2
Note on AF4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (V2 Ticket is completed, but that ticket in blocked state because our ticket is dependent on another ticket and another ticket is not completed yet.that ticket is related to LT india )
Note on AF5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (Its reopened mistaka by tonya)
Note on AF6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (Ticket is carry over because ticket ac had been changed)
Note on AF7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (V2 Ticket is completed, but that ticket in blocked state because our ticket is dependent on another ticket and another ticket is not completed yet.that ticket is related to LT india )
Note on AF12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (V2 Ticket is completed, but that ticket in blocked state because our ticket is dependent on another ticket and another ticket is not completed yet.that ticket is related to LT india )

## Detail6
Details for Sum of LT - Week Starting On: CET 05/19 - 06/02
Week Starting On | Planned story points | Actual delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio
CET 05/19 - 06/02 | 66 | 38 | 5 | 33 | 0 | 10 | 0 | 28 | 5 | 0 | 0.30303 | 0 | 0.84848 | 0

## Detail7
Details for Sum of LT - Week Starting On: CET 05/19 - 06/02
Week Starting On | Planned story points | Actual delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio
CET 05/19 - 06/02 | 66 | 38 | 5 | 37 | 0 | 10 | 0 | 28 | 5 | 0 | 0.30303 | 0 | 0.84848 | 0

## Consumer Experience Team
[8 empty] | Week Starting On | Planned story points | Actual delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio
[8 empty] | CET 03/24 - 04/07 | 106 | 73 | 2 | 71 | 0 | 11 | 5 | 28 | 2 | [5 empty] | Row Labels | Sum of V2 | Sum of LT | Row Labels | Sum of Rework | Sum of QA Passed |  | Green
PROJECT HEALTH DASHBOARD | [7 empty] | CET 04/07 - 04/21 | 103 | 56 | 10 | 46 | 0 | 18 | 0 | 47 | 10 | [5 empty] | CET 03/24 - 04/07 | 2 | 71 | CET 03/24 - 04/07 | 0 | 2 |  | Red
[8 empty] | CET 05/05 - 05/19 | 65 | 47 | 4 | 43 | 0 | 13 | 3 | 15 | 4 | [5 empty] | CET 04/07 - 04/21 | 10 | 46 | CET 04/07 - 04/21 | 0 | 10 |  | Amber
[8 empty] | CET 05/19 - 06/02 | 66 | 42 | 5 | 37 | 0 | 10 | 0 | 24 | 5 | [5 empty] | CET 05/05 - 05/19 | 4 | 43 | CET 05/05 - 05/19 | 0 | 4
[23 empty] | CET 05/19 - 06/02 | 5 | 37 | CET 05/19 - 06/02 | 0 | 5
| Project Name | LendingTree |  |  |  | Status Date | 2026-05-04 | [15 empty] | Grand Total | 21 | 197 | Grand Total | 0 | 21
| Sub Project | Consumer Experience Team (CET)
| Delivery Manager | Rajesh |  |  |  | Overall Status | Green
| Project Manager/Lead | Harpreet
| Client POC | Robert Ploeger
| Client Feedback | - | [20 empty] | Sprint | V2 | LT
Team Allocation
| Off-shore team | Allocated | 1+7 | Billable | 1
| On-site team | Allocated | 7 | [22 empty] | QA Passed
Rework
[23 empty] | Row Labels | Sum of LT Reopen Percentage | Sum of V2 Reopen Percentage |  | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[23 empty] | CET 03/24 - 04/07 | 0.15493 | 0 |  | CET 03/24 - 04/07 | 2.5 | 0.39437
[23 empty] | CET 04/07 - 04/21 | 0.3913 | 0 |  | CET 04/07 - 04/21 | 0 | 1.0217
[23 empty] | CET 05/05 - 05/19 | 0.30233 | 0 |  | CET 05/05 - 05/19 | 0.75 | 0.34884
[23 empty] | CET 05/19 - 06/02 | 0.27027 | 0 |  | CET 05/19 - 06/02 | 0 | 0.84848
[23 empty] | Grand Total | 1.1188 | 0 |  | Grand Total | 3.25 | 2.6134
[23 empty] | Sprint | V2 | LT | Sprint | V2 | LT
[26 empty] | Row Labels | Sum of Planned Vs Completed ratio
[26 empty] | CET 03/24 - 04/07 | 0.68868
[26 empty] | CET 04/07 - 04/21 | 0
[23 empty] | Sprint | V2 | LT | CET 05/05 - 05/19 | 0
[23 empty] | CET 03/24 - 04/07 | 2 | 71 | CET 05/19 - 06/02 | 0
[23 empty] | CET 04/07 - 04/21 | 10 | 46 | Grand Total | 0.68868
[23 empty] | CET 05/05 - 05/19 | 4 | 43
[23 empty] | CET 05/19 - 06/02 | 5 | 33
[26 empty] | Sprint | Planned Vs Completed ratio
[23 empty] | Sprint | V2 | LT
[23 empty] | CET 03/24 - 04/07 | 0 | 11
[23 empty] | CET 04/07 - 04/21 | 0 | 18
[23 empty] | CET 05/05 - 05/19 | 0 | 13
[23 empty] | CET 05/19 - 06/02 | 0 | 10
[23 empty] | Sprint | V2 | LT
[23 empty] | CET 03/24 - 04/07 | 5 | 28
[23 empty] | CET 04/07 - 04/21 | 0 | 47
[23 empty] | CET 05/05 - 05/19 | 3 | 15
[23 empty] | CET 05/19 - 06/02 | 0 | 28
Note on T1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered by V2.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered by LT.
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story points re-opened by external QA for V2 resources.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story Points Reopen by LT.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Carryover by LT.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total QA Passed by V2
Note on AF4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (V2 Ticket is completed, but that ticket in blocked state because our ticket is dependent on another ticket and another ticket is not completed yet.that ticket is related to LT india )
Note on AF5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (Its reopened mistaka by tonya)
Note on AF6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (Ticket is carry over because ticket ac had been changed)
Note on AF7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (V2 Ticket is completed, but that ticket in blocked state because our ticket is dependent on another ticket and another ticket is not completed yet.that ticket is related to LT india )
Note on AF12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (V2 Ticket is completed, but that ticket in blocked state because our ticket is dependent on another ticket and another ticket is not completed yet.that ticket is related to LT india )

## Phoenix - Forms
[8 empty] | Week Starting On | Planned Story Points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio | V2 InValid Reopen SP | Row Labels | Sum of V2 | Sum of LT |  | Row Labels | Sum of Rework | Sum of QA Passed
PROJECT HEALTH DASHBOARD | [7 empty] | 2025: PHX 07/1 - 07/31 | 51 | 51 | 14 |  | 2 | 5 | 0 | 0 | [6 empty] | 0 | 2025: PHX 12/1 - 12/31 | 21 | 29 |  | 2025: PHX 12/1 - 12/31 | 6 | 15 | Green
[8 empty] | 2025: PHX 08/1 - 08/31 | 41 | 41 | 13 |  | 3 | 4 | 0 | 0 | [6 empty] | 3 | 2026: PHX 01/1 - 01/31 | 17 | 50 |  | 2026: PHX 01/1 - 01/31 | 0 | 17 | Red
[8 empty] | 2025: PHX 09/1 - 09/30 | 36 | 36 | 10 | 26 | 0 | 2 | 0 | 0 | [7 empty] | 2026: PHX 2/1 - 2/28 | 11 | 36 |  | 2026: PHX 2/1 - 2/28 | 2 | 9 | Amber
[8 empty] | 2025: PHX 10/1 - 10/31 | 59 | 59 | 16 | 43 | 2 | 9 | 0 | 0 | [7 empty] | 2026: PHX 3/1 - 3/31 | 14 | 49 |  | 2026: PHX 3/1 - 3/31 | 2 | 12
| Project Name | LendingTree |  |  |  | Status Date | 2026-06-01 | 2025: PHX 11/1 - 11/30 | 68 | 68 | 17 |  | 3 | 9 | 0 | 0 | [6 empty] | 2 | 2026: PHX 4/1 - 4/30 | 21 | 58 |  | 2026: PHX 4/1 - 4/30 | 1 | 20
| Sub Project | Phoenix | [5 empty] | 2025: PHX 12/1 - 12/31 | 50 | 50 | 21 |  | 6 | 4 | 0 | 0 | [7 empty] | 2026: PHX 5/1 - 5/31 | 14 | 70 |  | 2026: PHX 5/1 - 5/31 | 3 | 11
| Delivery Manager | Rajesh |  |  |  | Overall Status | Green | 2026: PHX 01/1 - 01/31 | 67 | 67 | 17 |  | 0 | 2 | 0 | 0 | [7 empty] | Grand Total | 98 | 292 |  | Grand Total | 14 | 84
| Project Manager/Lead | Kunal Badgujar | [5 empty] | 2026: PHX 2/1 - 2/28 | 47 | 47 | 11 |  | 2 | 5 | 0 | 0
| Client POC | Douglas Brown | [5 empty] | 2026: PHX 3/1 - 3/31 | 63 | 63 | 14 |  | 2 | 10 | 0 | 0
| Client Feedback | - | [5 empty] | 2026: PHX 4/1 - 4/30 | 79 | 79 | 21 |  | 1 | 6 | 0 | 0 | [7 empty] | Sprint | V2 | LT |  | QA Passed
| Team Allocation | [6 empty] | 2026: PHX 5/1 - 5/31 | 84 | 84 | 14 |  | 3 | 27 | 0 | 0 | [11 empty] | Rework
| Off-shore team | Allocated | 1 | Billable | 1
| On-site team | Allocated | 7
[24 empty] | Row Labels | Sum of V2 Reopen Percentage | Sum of LT Reopen Percentage |  | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[24 empty] | 2025: PHX 12/1 - 12/31 | 0.28571 | 0.13793 |  | 2025: PHX 12/1 - 12/31 | 0 | 0
[24 empty] | 2026: PHX 01/1 - 01/31 | 0 | 0.04 |  | 2026: PHX 01/1 - 01/31 | 0 | 0
[24 empty] | 2026: PHX 2/1 - 2/28 | 0.18182 | 0.13889 |  | 2026: PHX 2/1 - 2/28 | 0 | 0 | n
[24 empty] | 2026: PHX 3/1 - 3/31 | 0.14286 | 0.20408 |  | 2026: PHX 3/1 - 3/31 | 0 | 0
[24 empty] | 2026: PHX 4/1 - 4/30 | 0.047619 | 0.10345 |  | 2026: PHX 4/1 - 4/30 | 0 | 0
[24 empty] | 2026: PHX 5/1 - 5/31 | 0.21429 | 0.38571 |  | 2026: PHX 5/1 - 5/31 | 0 | 0
[24 empty] | Grand Total | 0.87229 | 1.0101 |  | Grand Total | 0 | 0
[24 empty] | Sprint | V2 | LT |  | Sprint | V2 | LT
[24 empty] | Row Labels | Sum of Planned Vs Completed ratio |  | Sprint | V2 | LT
[24 empty] | 2025: PHX 12/1 - 12/31 | 1 |  | 2025: PHX 12/1 - 12/31 | 6 | 4
[24 empty] | 2026: PHX 01/1 - 01/31 | 1 |  | 2026: PHX 01/1 - 01/31 | 0 | 2
[24 empty] | 2026: PHX 2/1 - 2/28 | 1 |  | 2026: PHX 2/1 - 2/28 | 2 | 5
[24 empty] | 2026: PHX 3/1 - 3/31 | 1 |  | 2026: PHX 3/1 - 3/31 | 2 | 10
[24 empty] | 2026: PHX 4/1 - 4/30 | 1 |  | 2026: PHX 4/1 - 4/30 | 1 | 6
[24 empty] | 2026: PHX 5/1 - 5/31 | 1 |  | 2026: PHX 5/1 - 5/31 | 3 | 27
[24 empty] | Grand Total | 6
[24 empty] | Sprint | Sum of Planned Vs Completed Ratio
Note on S1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points planned during sprint planning.
Note on T1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points moved to PD.
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by V2 resources.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by LT resources.
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for V2 resources.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for LT resources.
Note on Y1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for V2 resources.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for LT resources.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered by V2 resources - Total number of story points re-opened.

## Flex
[8 empty] | Week Starting On | Planned Story Points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio | V2 InValid Reopen SP | Comments | Row Labels | Sum of V2 | Sum of LT | Row Labels | Sum of Rework | Sum of QA Passed
PROJECT HEALTH DASHBOARD | [7 empty] | Flex Sprint 13: 10/2 - 10/16 | 67 | 40 | 11 | 29 | 0 | 8 | 0 | 27 | [8 empty] | Flex '26 Sprint 5: 3/5 - 3/19 | 13 | 24 | Flex '26 Sprint 5: 3/5 - 3/19 | 0 | 13 | Green
[8 empty] | Flex Sprint 14: 10/16 - 10/30 | 58 | 43 | 4 | 39 | 0 | 0 | 2 | 13 | [8 empty] | Flex '26 Sprint 6: 3/19 - 4/2 | 8 | 21 | Flex '26 Sprint 6: 3/19 - 4/2 | 3 | 5 | Red
[8 empty] | Flex Sprint 15: 10/30 - 11/13 | 77 | 66 | 15 | 51 | 2 | 5 | 0 | 11 | [7 empty] | FLEX-657 was reopened due to a incorrect assumption by Product | Flex '26 Sprint 7: 4/2 - 4/16 | 3 | 44 | Flex '26 Sprint 7: 4/2 - 4/16 | 0 | 3 | Amber
[8 empty] | Flex Sprint 16: 11/13 - 12/4 | 56 | 40 | 10 | 30 | 0 | 13 | 5 | 11 | [8 empty] | Flex '26 Sprint 8: 4/16 - 4/30 | 8 | 33 | Flex '26 Sprint 8: 4/16 - 4/30 | 0 | 8
| Project Name | LendingTree |  |  |  | Status Date | 2026-06-01 | Flex Sprint 17: 12/4 - 12/18 | 71 | 54 | 8 | 46 | 0 | 10 | 2 | 15 | [7 empty] | FLEX-723: Carry over because started work 2 days before sprint end | Flex '26 Sprint 9: 4/30 - 5/14 | 3 | 34 | Flex '26 Sprint 9: 4/30 - 5/14 | 0 | 3
| Sub Project | FLEX | [5 empty] | Flex Sprint 18: 12/18 - 1/8 | 50 | 28 | 2 | 26 | 0 | 0 | 11 | 9 | [7 empty] | FLEX-712 was Dev Complete a week before sprint end, but it had dependency on FLEX-714, which did not move due to the holiday season. This led to a pile up and FLEX-715 and FLEX-717 was held up as well | Flex '26 Sprint10: 5/14 - 5/28 | 6 | 47 | Flex '26 Sprint10: 5/14 - 5/28 | 0 | 6
| Delivery Manager | Rajesh |  |  |  | Overall Status | Green | Flex '26 Sprint 1: 1/8 - 1/22 | 69 | 45 | 15 | 30 | 5 | 5 | 3 | 21 | [7 empty] | There was a carryover from previous sprint which explains the spike in completed story points. FLEX-712 was reopened due to a missing validation of invalid Guid's. It was fixed and completed within the sprint | Grand Total | 41 | 203 | Grand Total | 3 | 38
| Project Manager/Lead | Saurabh Chowdhury | [5 empty] | Flex '26 Sprint 2: 1/22 - 2/5 | 64 | 56 | 7 | 49 | 0 | 8 | 0 | 8 | [7 empty] | FLEX-751 was an invalid reopen by PM to close ticket
| Client POC | David Wilson | [5 empty] | Flex '26 Sprint 3: 2/5 - 2/19 | 55 | 41 | 5 | 36 | 0 | 2 | 3 | 11 | [7 empty] | FLEX-828 of 3 story points, could have been completed, but Product did not UAT for 5 days. It was moved to UAT on 17th Feb and moved to PD on 26th Feb
| Client Feedback | - | [5 empty] | Flex '26 Sprint 4: 2/19 - 3/5 | 64 | 46 | 4 | 30 | 3 | 0 | 12 | 6 | [7 empty] | FLEX-839,839,840 carried over due to mismatch between Figma design and Ticket AC. Some changes in Figma were not mentioned in the AC | Sprint | V2 | LT | QA Passed
| Team Allocation | [6 empty] | Flex '26 Sprint 5: 3/5 - 3/19 | 53 | 37 | 13 | 24 | 0 | 2 | 0 | 16 | [11 empty] | Rework
| Off-shore team | Allocated | 1 | Billable | 1 |  |  | Flex '26 Sprint 6: 3/19 - 4/2 | 55 | 29 | 8 | 21 | 3 | 5 | 0 | 26
| On-site team | Allocated | 1 |  |  |  |  | Flex '26 Sprint 7: 4/2 - 4/16 | 54 | 47 | 3 | 44 | 0 | 4 | 2 | 5
[8 empty] | Flex '26 Sprint 8: 4/16 - 4/30 | 54 | 41 | 8 | 33 | 0 | 6 | 0 | 11
[8 empty] | Flex '26 Sprint 9: 4/30 - 5/14 | 42 | 37 | 3 | 34 | 0 | 2 | 0 | 5
[8 empty] | Flex '26 Sprint10: 5/14 - 5/28 | 63 | 53 | 6 | 47 | 0 | 6 | 4 | 6
[25 empty] | Row Labels | Sum of V2 Reopen Percentage | Sum of LT Reopen Percentage | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[25 empty] | Flex '26 Sprint 5: 3/5 - 3/19 | 0 | 0.083333 | Flex '26 Sprint 5: 3/5 - 3/19 | 0 | 0.66667
[25 empty] | Flex '26 Sprint 6: 3/19 - 4/2 | 0.375 | 0.2381 | Flex '26 Sprint 6: 3/19 - 4/2 | 0 | 1.2381
[25 empty] | Flex '26 Sprint 7: 4/2 - 4/16 | 0 | 0.090909 | Flex '26 Sprint 7: 4/2 - 4/16 | 0.66667 | 0.11364
[25 empty] | Flex '26 Sprint 8: 4/16 - 4/30 | 0 | 0.18182 | Flex '26 Sprint 8: 4/16 - 4/30 | 0 | 0.33333
[25 empty] | Flex '26 Sprint 9: 4/30 - 5/14 | 0 | 0.058824 | Flex '26 Sprint 9: 4/30 - 5/14 | 0 | 0.14706
[25 empty] | Flex '26 Sprint10: 5/14 - 5/28 | 0 | 0.12766 | Flex '26 Sprint10: 5/14 - 5/28 | 0.66667 | 0.12766
[25 empty] | Grand Total | 0.375 | 0.78064 | Grand Total | 1.3333 | 2.6264
[25 empty] | Sprint | V2 | LT | Sprint | V2 | LT
[25 empty] | Row Labels | Sum of Planned Vs Completed ratio
[25 empty] | Flex '26 Sprint 5: 3/5 - 3/19 | 0.69811
[25 empty] | Flex '26 Sprint 6: 3/19 - 4/2 | 0.52727
[25 empty] | Flex '26 Sprint 7: 4/2 - 4/16 | 0.87037
[25 empty] | Flex '26 Sprint 8: 4/16 - 4/30 | 0.75926
[25 empty] | Flex '26 Sprint 9: 4/30 - 5/14 | 0.88095
[25 empty] | Flex '26 Sprint10: 5/14 - 5/28 | 0.84127
[25 empty] | Grand Total | 4.5772
[25 empty] | Sprint | Sum of Planned Vs Completed Ratio |  | Sprint | V2 | LT
[28 empty] | Flex '26 Sprint 5: 3/5 - 3/19 | 0 | 2
[28 empty] | Flex '26 Sprint 6: 3/19 - 4/2 | 3 | 5
[28 empty] | Flex '26 Sprint 7: 4/2 - 4/16 | 0 | 4
[28 empty] | Flex '26 Sprint 8: 4/16 - 4/30 | 0 | 6
[28 empty] | Flex '26 Sprint 9: 4/30 - 5/14 | 0 | 2
[28 empty] | Flex '26 Sprint10: 5/14 - 5/28 | 0 | 6
[28 empty] | Sprint | V2 | LT
[28 empty] | Flex '26 Sprint 5: 3/5 - 3/19 | 0 | 16
[28 empty] | Flex '26 Sprint 6: 3/19 - 4/2 | 0 | 26
[28 empty] | Flex '26 Sprint 7: 4/2 - 4/16 | 2 | 5
[28 empty] | Flex '26 Sprint 8: 4/16 - 4/30 | 0 | 11
[28 empty] | Flex '26 Sprint 9: 4/30 - 5/14 | 0 | 5
[28 empty] | Flex '26 Sprint10: 5/14 - 5/28 | 4 | 6
Note on S1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points planned during sprint planning.
Note on T1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points moved to PD.
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by V2 resources.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by LT resources.
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for V2 resources.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for LT resources.
Note on Y1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for V2 resources.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for LT resources.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered by V2 resources - Total number of story points re-opened.
Note on AD9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: V2 carryover is increased due to Christmas vacations team members were on leave.

## Detail2 (hidden)
Details for Sum of V2 - Week Starting On: 2022: PHX 7/28 - 8/11
Week Starting On | Planned Story Points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed
2022: PHX 7/28 - 8/11 | 32 | 27 | 10 | 29 | 0 | 2 | 3 | 2 | 3

## Pre-Prime (hidden)
[8 empty] | Week Starting On | Planned story points | Actual delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio | Sprint velocity | Row Labels | Sum of V2 | Sum of LT | Row Labels | Sum of Rework | Sum of QA Passed
PROJECT HEALTH DASHBOARD | [7 empty] | 2022: SUB 01/04 - 01/18 | 13 |  | 11 | 2 | 0 | 0 | 0 | 0 | [7 empty] | 2022: OCR 7.5 - 7.19 | 8 | 24 | 2022: OCR 7.5 - 7.19 | 0 | 8 | Green
[8 empty] | 2022: OCR 01/18 - 02/01 | 57 |  | 10 | 47 | 0 | 14 | 5 | 16 | [7 empty] | 2022: OCR 7.19 - 8.2 | 7 | 22 | 2022: OCR 7.19 - 8.2 | 0 | 7 | Red
[8 empty] | 2022: OCR 3/1 - 3/15 | 49 |  | 5 | 44 | 0 | 19 | 0 | 8 | [7 empty] | 2022: OCR 8.2 - 8.16 | 6 | 37 | 2022: OCR 8.2 - 8.16 | 0 | 6 | Amber
[8 empty] | 2022: OCR 3/15 - 3/29 | 50 |  | 10 | 40 | 0 | 10 | 0 | 13 | [7 empty] | 2022: CS 8.16 - 8.30 | 15 | 35 | 2022: CS 8.16 - 8.30 | 0 | 15
| Project Name | LendingTree |  |  |  | Status Date | 2022-11-09 | 2022: OCR 3/29 - 4/12 | 44 |  | 6 | 34 | 2 | 8 | 0 | 17 | [7 empty] | 2022: CS 8.30 - 9.13 | 10 | 33 | 2022: CS 8.30 - 9.13 | 5 | 5
| Sub Project | Pre-Prime | [5 empty] | 2022: OCR 4/12 - 4/26 | 54 |  | 5 | 49 | 0 | 9 | 0 | 9 | [7 empty] | 2022: CS 9.13 - 9.27 | 11 | 28 | 2022: CS 9.13 - 9.27 | 0 | 11
| Delivery Manager | Mamatha |  |  |  | Overall Status | Green | 2022: OCR 4/26 - 5/10 | 54 |  | 7 | 47 | 0 | 4 | 5 | 14 | [7 empty] | Grand Total | 57 | 179 | Grand Total | 5 | 52
| Project Manager/Lead | Disha | [5 empty] | 2022: OCR 5/10 - 5/24 | 48 |  | 9 | 39 | 0 | 4 | 3 | 14
| Client POC | - | [5 empty] | 2022: OCR 5.24 - 6.7 | 37 |  | 3 | 34 | 0 | 2 | 0 | 8
| Client Feedback | - | [5 empty] | 2022: OCR 6.7 - 6.21 | 38 |  | 8 | 30 | 0 | 2 | 2 | 9
| Team Allocation | [6 empty] | 2022: OCR 6.21 - 7.5 | 37 |  | 10 | 27 | 0 | 3 | 5 | 3 | [7 empty] | Sprint | V2 | LT | QA Passed
| Off-shore team | Allocated | 1 | Billable | 1 |  |  | 2022: OCR 7.5 - 7.19 | 32 |  | 8 | 24 | 0 | 0 | 2 | 6 | [10 empty] | Rework
| On-site team | Allocated | 8 |  |  |  |  | 2022: OCR 7.19 - 8.2 | 29 |  | 7 | 22 | 0 | 0 | 0 | 8
[8 empty] | 2022: OCR 8.2 - 8.16 | 43 |  | 6 | 37 | 0 | 3 | 5 | 20
[8 empty] | 2022: CS 8.16 - 8.30 | 50 |  | 15 | 35 | 0 | 5 | 10 | 21
[8 empty] | 2022: CS 8.30 - 9.13 | 43 |  | 10 | 33 | 5 | 4 | 0 | 20
[8 empty] | 2022: CS 9.13 - 9.27 | 39 |  | 11 | 28 | 0 | 4 | 8 | 15
[8 empty] | 2022: CS 9.27 - 10.11 | 40 |  | 15 | 25 | 0 | 11 | 0 | 15
[24 empty] | Row Labels | Sum of V2 Reopen Percentage | Sum of LT Reopen Percentage | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[24 empty] | 2022: OCR 7.5 - 7.19 | 0 | 0 | 2022: OCR 7.5 - 7.19 | 0.25 | 0.25
[24 empty] | 2022: OCR 7.19 - 8.2 | 0 | 0 | 2022: OCR 7.19 - 8.2 | 0 | 0.36364
[24 empty] | 2022: OCR 8.2 - 8.16 | 0 | 0.081081 | 2022: OCR 8.2 - 8.16 | 0.83333 | 0.54054
[24 empty] | 2022: CS 8.16 - 8.30 | 0 | 0.14286 | 2022: CS 8.16 - 8.30 | 0.66667 | 0.6
[24 empty] | 2022: CS 8.30 - 9.13 | 0.5 | 0.12121 | 2022: CS 8.30 - 9.13 | 0 | 0.60606
[24 empty] | 2022: CS 9.13 - 9.27 | 0 | 0.14286 | 2022: CS 9.13 - 9.27 | 0.72727 | 0.53571
[24 empty] | Grand Total | 0.5 | 0.48801 | Grand Total | 2.4773 | 2.896
[24 empty] | Sprint | V2 | LT | Sprint | V2 | LT
[24 empty] | Row Labels | Sum of Planned Vs Completed ratio
[24 empty] | 2022: OCR 7.5 - 7.19 | 0.75
[24 empty] | 2022: OCR 7.19 - 8.2 | 0.72414
[24 empty] | 2022: OCR 8.2 - 8.16 | 0.4186
[24 empty] | 2022: CS 8.16 - 8.30 | 0.38
[24 empty] | 2022: CS 8.30 - 9.13 | 0.53488
[24 empty] | 2022: CS 9.13 - 9.27 | 0.41026
[24 empty] | Grand Total | 3.2179
[24 empty] | Sprint | Planned Vs Completed ratio
Note on T1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sprint name
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points planned during sprint planning.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered by V2.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered by LT.
Note on Y1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story Points Reopen by V2.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story Points Reopen by LT.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Carryover by V2.
Note on AB1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Carryover by LT.
Note on AC1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total QA Passed by V2
Note on T10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Disha Rai Please add sprint data for June, July, Aih 2022 montths CC: @Mamatha Joshi Reply: Done
Note on I13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Babitha is added as a buffer resource.
Note on AA13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Issue added after current sprint task was done
Note on AA15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Waited for couple of days for code review from Lew
Note on AA16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CS-526 - Was added at last day of sprint as current work was done. CS-34 - Was blocked as the last build pushed was not being installed
Note on AD17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dynamic data was not fit in given modal size and was on leave so it got reopened.
Note on AA18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CS-6380- Got carried over as Mark was on leave and ticket was waiting for UAT. CS-518: Was added on last day of sprint as additional ticket

## Sheet1 (hidden)
Week Starting On | Planned Story points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio
Velarium Spt 7.2 ¦ 7.13-7.27 | 20 | 20 | 1 | 19 | 0 | 4 | 0 | 0 | 1 | 0 | 0.21053 | 0 | 0 | 1
Velarium Spt 7.3 ¦ 7.27-8.10 | 23 | 23 | 4 | 19 | 0 | 2 | 0 | 0 | 4 | 0 | 0.10526 | 0 | 0 | 1
Velarium Spt 8.1 ¦ 8.10-8.24 | 19 | 19 | 5 | 14 | 0 | 2 | 0 | 0 | 5 | 0 | 0.14286 | 0 | 0 | 1
Velarium Spt 8.2 ¦ 8.24-9.7 | 29 | 29 | 6 | 23 | 2 | 3 | 0 | 0 | 4 | 0.33333 | 0.13043 | 0 | 0 | 1
Velarium Spt 9.1 ¦ 9.7-9.21 | 31 | 31 | 7 | 24 | 0 | 5 | 0 | 0 | 7 | 0 | 0.20833 | 0 | 0 | 1
Velarium Spt 9.2 ¦ 9.21-10.5 | 21 | 21 | 5 | 16 | 3 | 7 | 0 | 0 | 2 | 0.6 | 0.4375 | 0 | 0 | 1

## Partner Central (hidden)
[8 empty] | Week Starting On | Planned Story points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio | Row Labels | Sum of V2 | Sum of LT | Row Labels | Sum of Rework | Sum of QA Passed | Row Labels | Sum of V2 Reopen Percentage | Sum of LT Reopen Percentage |  | Row Labels | Sum of V2 Reopen Percentage | Sum of LT Reopen Percentage
PROJECT HEALTH DASHBOARD | [7 empty] | PART 2021: 3.1 (3.10 - 3.24) | 25 | 4 | 0 | 4 | 0 | 0 | 12 | 9 |  | 0% |  | 100% |  |  | Velarium Spt 7.2 ¦ 7.13-7.27 | 1 | 19 | Velarium Spt 7.2 ¦ 7.13-7.27 | 0 | 1 | Velarium Spt 7.2 ¦ 7.13-7.27 | 0% | 21.05% | Green | PART 2021: 3.1 (3.10 - 3.24) | 0% | 0
[8 empty] | PART 2021: 3.2 (3.24 - 4.7) | 41 | 25 | 10 | 15 | 10 | 1 | 8 | 8 | [6 empty] | Velarium Spt 7.3 ¦ 7.27-8.10 | 4 | 19 | Velarium Spt 7.3 ¦ 7.27-8.10 | 0 | 4 | Velarium Spt 7.3 ¦ 7.27-8.10 | 0% | 10.53% | Red | PART 2021: 3.2 (3.24 - 4.7) | 50% | 0.066667
[8 empty] | PART 2021: 4.1 (4.7 - 4.21) | 42 | 14 | 3 | 11 | 0 | 8 | 15 | 13 | [6 empty] | Velarium Spt 8.1 ¦ 8.10-8.24 | 5 | 14 | Velarium Spt 8.1 ¦ 8.10-8.24 | 0 | 5 | Velarium Spt 8.1 ¦ 8.10-8.24 | 0% | 14.29% | Amber | PART 2021: 4.1 (4.7 - 4.21) | 0% | 0.72727
[8 empty] | PART 2021: 4.2 (4.21 - 5.5) | 63 | 23 | 4 | 19 | 4 | 8 | 20 | 20 | [6 empty] | Velarium Spt 8.2 ¦ 8.24-9.7 | 6 | 23 | Velarium Spt 8.2 ¦ 8.24-9.7 | 2 | 4 | Velarium Spt 8.2 ¦ 8.24-9.7 | 33.33% | 13.04% |  | PART 2021: 4.2 (4.21 - 5.5) | 50% | 0.42105
| Project Name | LendingTree |  |  |  | Status Date | 2022-12-01 | PART 2021: 5.1 (5.5 - 5.19) | 67 | 41 | 16 | 25 | 12 | 11 | 6 | 20 | 4 | [5 empty] | Velarium Spt 9.1 ¦ 9.7-9.21 | 7 | 24 | Velarium Spt 9.1 ¦ 9.7-9.21 | 0 | 7 | Velarium Spt 9.1 ¦ 9.7-9.21 | 0% | 20.83% |  | Grand Total | 100% | 1.215
| Sub Project | Partner Central | [5 empty] | PART 2021: 5.2 (5.20 - 6.2) | 56 | 33 | 20 | 13 | 8 | 1 | 6 | 17 | 12 | [5 empty] | Velarium Spt 9.2 ¦ 9.21-10.5 | 5 | 16 | Velarium Spt 9.2 ¦ 9.21-10.5 | 3 | 2 | Velarium Spt 9.2 ¦ 9.21-10.5 | 60% | 43.75%
| Delivery Manager | Mamatha |  |  |  | Overall Status | Green | PART 2021: 6.1 (6.2 - 6.16) | 44 | 22 | 7 | 15 | 2 | 3 | 7 | 15 | 5 | [5 empty] | Grand Total | 28 | 115 | Grand Total | 5 | 23 | Grand Total | 93.33% | 123.5%
| Project Manager/Lead | Goutham V | [5 empty] | PART 2021: 6.2 (6.16 - 6.30) | 57 | 25 | 9 | 16 | 5 | 7 | 8 | 24 | 4
| Client POC | Kerry | [5 empty] | PART 2021: 7.1 (6.30 - 7.14) | 55 | 25 | 11 | 14 | 8 | 6 | 6 | 24 | 3
| Client Feedback | - | [5 empty] | PART 2021: 7.2 (7.14 - 7.28) | 49 | 30 | 5 | 25 | 1 | 9 | 6 | 13 | 4 | [5 empty] | Sprint | V2 | LT | QA Passed |  |  | Sprint | V2 | LT
| Team Allocation | [6 empty] | PART 2021: 8.1 (7.28 - 8.11) | 44 | 22 | 8 | 14 | 6 | 9 | 8 | 15 | 2 | [8 empty] | Rework
| Off-shore team | Allocated | 1 | Billable | 1 |  |  | PART 2021: 8.2 (8.11 - 8.25) | 49 | 28 | 9 | 19 | 5 | 4 | 7 | 14 | 4
| On-site team | Allocated | [5 empty] | PART 2021: 9.1 (8.25 - 9.8) | 60 | 34 | 7 | 27 | 0 | 7 | 11 | 15 | 7
[8 empty] | PART 2021: 9.2 (9.8 - 9.22) | 49 | 27 | 4 | 23 | 0 | 8 | 11 | 11 | 4
[8 empty] | PART 2021: 9.3 (9.22 - 10.6) | 52 | 29 | 18 | 11 | 9 | 2 | 9 | 14 | 9
[8 empty] | PART 2021: 10.1 (10.6 - 10.20) | 50 | 39 | 18 | 21 | 2 | 5 | 6 | 5 | 16
[8 empty] | PART 2021: 10.2 (10.20 - 11.3) | 60 | 43 | 16 | 27 | 2 | 5 | 3 | 14 | 14 | [5 empty] | PART 2021: 8.2 (8.11 - 8.25)
[8 empty] | PART 2021: 11.1 (11.3 - 11.17) | 42 | 24 | 5 | 19 | 4 | 3 | 6 | 12 | 1
[8 empty] | PART 2021: 11.2 (11.17- 12.1) | 58 | 33 | 10 | 23 | 2 | 1 | 5 | 20 | 8
[8 empty] | PART 2021: 12.1 (12.1 - 12.15) | 53 | 31 | 8 | 23 | 4 | 4 | 6 | 16 | 4 | [11 empty] | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[8 empty] | PART 2021 12.2 (12.15 - 1.5) | 41 | 21 | 13 | 8 | 3 | 0 | 4 | 16 | 10 | [5 empty] | Row Labels | Sum of Planned Vs Completed ratio |  |  |  |  | Velarium Spt 7.2 ¦ 7.13-7.27 | 0 | 0
[8 empty] | PART 2022 1.1 (1.5 - 1.12) | 31 | 20 | 3 | 17 | 0 | 8 | 2 | 9 | 0 | [5 empty] | Velarium Spt 7.2 ¦ 7.13-7.27 | 1 |  |  |  |  | Velarium Spt 7.3 ¦ 7.27-8.10 | 0 | 0
[8 empty] | PART 2022 1.2 (1.12 - 1.26) | 28 | 19 | 6 | 13 | 2 | 3 | 2 | 7 | 4 | [5 empty] | Velarium Spt 7.3 ¦ 7.27-8.10 | 1 |  |  |  |  | Velarium Spt 8.1 ¦ 8.10-8.24 | 0 | 0
[8 empty] | PART 2022 2.1 (1.26 - 2.9) | 22 | 11 | 0 | 11 | 0 | 0 | 7 | 4 | 0 | [5 empty] | Velarium Spt 8.1 ¦ 8.10-8.24 | 1 |  |  |  |  | Velarium Spt 8.2 ¦ 8.24-9.7 | 0 | 0
[8 empty] | PART 2022 2.2 (2.9 - 2.23) | 31 | 13 | 5 | 8 | 0 | 2 | 6 | 12 | 5 | [5 empty] | Velarium Spt 8.2 ¦ 8.24-9.7 | 1 |  |  |  |  | Velarium Spt 9.1 ¦ 9.7-9.21 | 0 | 0
[8 empty] | PART 2022 3.1 (2.23 - 3.9) | 27 | 18 | 8 | 10 | 4 | 0 | 3 | 6 | 4 | [5 empty] | Velarium Spt 9.1 ¦ 9.7-9.21 | 1 |  |  |  |  | Velarium Spt 9.2 ¦ 9.21-10.5 | 0 | 0
[8 empty] | PART 2022 3.2 (3.9 - 3.23) | 14 | 14 | 9 | 5 | 2 | 0 | 0 | 0 | 7 | [5 empty] | Velarium Spt 9.2 ¦ 9.21-10.5 | 1 |  |  |  |  | Grand Total | 0 | 0
[8 empty] | PART 2022 3.3 (3.23 - 4.6) | 12 | 9 | 0 | 9 | 0 | 0 | 0 | 3 | 0 | [5 empty] | Grand Total | 6
[8 empty] | PART 2022 4.1 ¦ 4.6-4.20 | 20 | 20 | 4 | 16 | 2 | 5 | 0 | 0 | 2
[8 empty] | PART Sprint 4.2 ¦ 4.20-5.4 | 34 | 31 | 8 | 23 | 2 | 0 | 0 | 3 | 6 | [11 empty] | Sprint | V2 | LT
[8 empty] | PB Sprint 5.1 ¦ 5.4-5.18 | 29 | 29 | 4 | 25 | 0 | 11 | 0 | 0 | 4 | [5 empty] | Sprint | Planned Vs Completed ratio
[8 empty] | PB Sprint 5.2 ¦ 5.18-6.1 | 20 | 20 | 2 | 18 | 0 | 9 | 0 | 0 | 2
[8 empty] | PART Sprint 6.1 ¦ 6.1-6.15 | 21 | 21 | 6 | 15 | 6 | 4 | 0 | 0 | 0
[8 empty] | Velarium Spt 6.2 ¦ 6.15-6.29 | 17 | 17 | 3 | 14 | 2 | 12 | 0 | 0 | 1
[8 empty] | Velarium Spt 7.1 ¦ 6.29-7.13 | 18 | 18 | 0 | 18 | 0 | 8 | 0 | 0 | 0
[8 empty] | Velarium Spt 7.2 ¦ 7.13-7.27 | 20 | 20 | 1 | 19 | 0 | 4 | 0 | 0 | 1
[8 empty] | Velarium Spt 7.3 ¦ 7.27-8.10 | 23 | 23 | 4 | 19 | 0 | 2 | 0 | 0 | 4
[8 empty] | Velarium Spt 8.1 ¦ 8.10-8.24 | 19 | 19 | 5 | 14 | 0 | 2 | 0 | 0 | 5
[8 empty] | Velarium Spt 8.2 ¦ 8.24-9.7 | 29 | 29 | 6 | 23 | 2 | 3 | 0 | 0 | 4
[8 empty] | Velarium Spt 9.1 ¦ 9.7-9.21 | 31 | 31 | 7 | 24 | 0 | 5 | 0 | 0 | 7
[8 empty] | Velarium Spt 9.2 ¦ 9.21-10.5 | 21 | 21 | 5 | 16 | 3 | 7 | 0 | 0 | 2
[8 empty] | Velarium Spt 10.2 ¦ 10.19-11.2 | 17 | 17 | 5 | 12 | 3 | 2 | 0 | 0 | 2
[8 empty] | Velarium Spt 11.1 ¦ 11.2-11.16 | 16 | 16 | 8 | 8 | 3 | 0 | 0 | 0 | 5
[8 empty] | Velarium Sp 11.2 ¦ 11.16-11.30 | 53 | 53 | 14 | 39 | 4 | 8 | 0 | 0 | 10
Note on T1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sprint name
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points planned during sprint planning.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points moved to PD.
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by V2 resources.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by LT resources.
Note on Y1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for V2 resources.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for LT resources.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for V2 resources.
Note on AB1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for LT resources.
Note on AC1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered by V2 resources - Total number of story points re-opened.
Note on AD1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by V2 resources Over Total number of story points re-opened.
Note on AE1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by LT resources over Total number of story points re-opened.
Note on AF1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by V2 resources over Total number of story points carry-over.
Note on AG1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by LT resources over Total number of story points carry-over.
Note on W4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: API and Infrastructure dependency this will be better managed in upcoming sprints
Note on AF4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Project newly started Infrastructure was not ready OTA dependency API dependency
Note on W5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: API and Infrastructure dependency this will be better managed in upcoming sprints
Note on AD5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: - Change in requirement as this is new project - Complex functionality
Note on AF5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Project newly started Infrastructure was not ready OTA dependency API dependency
Note on I13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vishal is a shared resource for Canopy and Partner Central.
Note on AF14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Prasad was on leave and Goutham took some of his tickets.
Note on AF15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Prasad moved out and Subha added in the team as a new member.
Note on AD16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New feature which is why the requirements was changing.

## Detail1 (hidden)
Details for Sum of V2 - Week Starting On: 2022: PHX 8/11 - 8/25
Week Starting On | Planned Story Points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed
2022: PHX 8/11 - 8/25 | 25 | 22 | 5 | 20 | 0 | 2 | 1 | 3 | 5

## Web Analytics (hidden)
[8 empty] | Week Starting On | Planned Story Points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio | Old Dates | Row Labels | Sum of V2 | Sum of LT | Row Labels | Sum of Rework | Sum of QA Passed
PROJECT HEALTH DASHBOARD | [7 empty] | DWA: 12/27 - 01/03 2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | [7 empty] | DWA: 11/20 - 11/26 2022 | 0 | 5
[8 empty] | DWA: 01/03 - 01/10 2022 | 10 | 10 | 4 | 0 | 1 | 0 | 0 | 0 |  |  | 0% | [7 empty] | DWA: 11/27 - 12/03 2022 | 0 | 3
[8 empty] | DWA: 01/10 - 01/17 2022 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | [7 empty] | DWA: 12/04 - 12/10 2022 | 0 | 3
[8 empty] | DWA: 01/17 - 01/24 2022 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | [7 empty] | DWA: 12/11 - 12/17 2022 | 0 | 1
| Project Name | LendingTree |  |  |  | Status Date | 2022-11-30 | DWA: 01/24 - 01/31 2022 | 9 | 9 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | [7 empty] | Grand Total | 0 | 12
| Sub Project | Thundercats | [5 empty] | DWA: 01/31 - 02/07 2022 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
| Delivery Manager | Mamatha Joshi |  |  |  | Overall Status | Green | DWA: 02/07 - 02/14 2022 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
| Project Manager/Lead | Mamatha Joshi | [5 empty] | DWA: 02/14 - 02/21 2022 | 11 | 11 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
| Client POC | - | [5 empty] | DWA: 02/21 - 02/28 2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
| Client Feedback | - | [5 empty] | DWA: 02/28 - 03/07 2022 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
| Team Allocation | [6 empty] | DWA: 03/07 - 03/14 2022 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
| Off-shore team | Allocated | 1 | Billable | 1 |  |  | DWA: 03/14 - 03/21 2022 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
| On-site team | Allocated | 0 |  |  |  |  | DWA: 03/21 - 03/28 2022 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 03/28 - 04/04 2022 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 04/04 - 04/11 2022 | 12 | 12 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 04/11 - 04/18 2022 | 5 | 5 | 0 | 2 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 04/18 - 04/25 2022 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 04/25 - 05/02 2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  |  |  | Kanban Week | V2 | LT | QA Passed | 100
[8 empty] | DWA: 05/02 - 05/09 2022 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | [7 empty] | Rework
[8 empty] | DWA: 05/09 - 05/16 2022 | 9 | 9 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 05/16 - 05/23 2022 | 13 | 13 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 05/23 - 05/30 2022 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 05/29 - 06/04 2022 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 06/05 - 06/11 2022 | 12 | 12 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 06/12 - 06/18 2022 | 7 | 7 | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 06/19 - 06/25 2022 | 9 | 9 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 06/26 - 07/02 2022 | 12 | 12 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 07/03 - 07/09 2022 | 9 | 9 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 07/10 - 07/16 2022 | 9 | 9 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 07/17 - 07/23 2022 | 14 | 14 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 07/24 - 07/30 2022 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 07/31 - 08/06 2022 | 6 | 6 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 08/07 - 08/13 2022 | 11 | 11 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 08/14 - 08/20 2022 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 08/21 - 08/27 2022 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 08/28 - 09/03 2022 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  |  |  | Row Labels | Sum of V2 Reopen Percentage | Sum of LT Reopen Percentage | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[8 empty] | DWA: 09/04 - 09/10 2022 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 09/11 - 09/17 2022 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 09/18 - 09/24 2022 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 09/25 - 10/01 2022 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 10/02 - 10/08 2022 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 10/09 - 10/15 2022 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 10/16 - 10/22 2022 | 20 | 20 | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 10/23 - 10/29 2022 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 10/30 - 11/05 2022 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 11/06 - 11/12 2022 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 11/13 - 11/19 2022 | 10 | 10 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 11/20 - 11/26 2022 | 11 | 11 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 11/27 - 12/03 2022 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 12/04 - 12/10 2022 | 5 | 5 | 3 | 2 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 12/11 - 12/17 2022 | 6 | 6 | 1 | 5 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 12/18 - 12/24 2022 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 |  |  | 0%
[8 empty] | DWA: 12/25 - 12/31 2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  |  |  | Sprint | V2 | LT | Sprint | V2 | LT
[24 empty] | Row Labels | Sum of Planned Vs Completed ratio
Grand Total
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0%
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0%
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points planned during sprint planning.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points moved to PD.
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by V2 resources.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by LT resources.
Note on Y1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for V2 resources.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for LT resources.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for V2 resources.
Note on AB1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for LT resources.
Note on AC1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered by V2 resources - Total number of story points re-opened.
Note on AD54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Invalid re-open

## Mortgage Purchase (hidden)
[8 empty] | Week Starting On | Planned Story Points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio | Row Labels | Sum of V2 | Sum of LT | Row Labels | Sum of Rework | Sum of QA Passed
PROJECT HEALTH DASHBOARD | [22 empty] | Mortgage Purchase Sprint 8 | 10 | 39 | Mortgage Purchase Sprint 8 | 0 | 10 | Green
[8 empty] | Mortgage Purchase Sprint 0 | 7 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | [6 empty] | Mortgage Purchase Sprint 9 | 13 | 39 | Mortgage Purchase Sprint 9 | 3 | 10 | Red
[8 empty] | Mortgage Purchase Sprint 1 | 28 | 15 | 2 | 26 | 0 | 0 | 0 | 13 | [6 empty] | Mortgage Purchase Sprint 10 | 13 | 32 | Mortgage Purchase Sprint 10 | 5 | 8 | Amber
[8 empty] | Mortgage Purchase Sprint 2 | 50 | 38 | 11 | 39 | 0 | 5 | 0 | 12 | [6 empty] | Mortgage Purchase Sprint 11 | 17 | 23 | Mortgage Purchase Sprint 11 | 7 | 10
| Project Name | LendingTree |  |  |  | Status Date | 2021-12-27 | Mortgage Purchase Sprint 3 | 59 | 59 | 21 | 38 | 0 | 19 | 0 | 0 | [6 empty] | Mortgage Purchase Sprint 12 | 6 | 30 | Mortgage Purchase Sprint 12 | 0 | 6
| Sub Project | Mortgage Purchase | [5 empty] | Mortgage Purchase Sprint 4 | 75 | 75 | 35 | 40 | 7 | 3 | 0 | 0 | [6 empty] | Mortgage Purchase Sprint 13 | 17 | 21 | Mortgage Purchase Sprint 13 | 3 | 14
| Delivery Manager | Mamatha |  |  |  | Overall Status | Green | Mortgage Purchase Sprint 5 |  | 40 | 6 | 38 | 0 | 0 | 3 | 1 | [6 empty] | Mortgage Purchase Sprint 14 | 12 | 17 | Mortgage Purchase Sprint 14 | 2 | 10
| Project Manager/Lead | Payal | [5 empty] | Mortgage Purchase Sprint 6 | 46 | 45 | 10 | 36 | 0 | 0 | 0 | 1 | [6 empty] | Grand Total | 88 | 201 | Grand Total | 20 | 68
| Client POC | - | [5 empty] | Mortgage Purchase Sprint 7 | 50 | 48 | 11 | 39 | 8 | 17 | 0 | 2
| Client Feedback | - | [5 empty] | Mortgage Purchase Sprint 8 | 49 | 31 | 10 | 39 | 0 | 12 | 5 | 13 | [6 empty] | Sprint | V2 | LT | QA Passed
| Team Allocation | [6 empty] | Mortgage Purchase Sprint 9 | 52 | 46 | 13 | 39 | 3 | 21 | 0 | 6 | [9 empty] | Rework
| Off-shore team | Allocated | 3 | Billable | 3 |  |  | Mortgage Purchase Sprint 10 | 45 | 36 | 13 | 32 | 5 | 7 | 5 | 4
| On-site team | Allocated | [5 empty] | Mortgage Purchase Sprint 11 | 40 | 27 | 17 | 23 | 7 | 8 | 3 | 10
[8 empty] | Mortgage Purchase Sprint 12 | 36 | 31 | 6 | 30 | 0 | 6 | 0 | 5
[8 empty] | Mortgage Purchase Sprint 13 | 38 | 38 | 17 | 21 | 3 | 4 | 0 | 0
[8 empty] | Mortgage Purchase Sprint 14 | 29 | 26 | 12 | 17 | 2 | 2 | 3 | 0
[23 empty] | Row Labels | Sum of V2 Reopen Percentage | Sum of LT Reopen Percentage | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[23 empty] | Mortgage Purchase Sprint 8 | 0 | 0.30769 | Mortgage Purchase Sprint 8 | 0.5 | 0.33333
[23 empty] | Mortgage Purchase Sprint 9 | 0.23077 | 0.53846 | Mortgage Purchase Sprint 9 | 0 | 0.15385
[23 empty] | Mortgage Purchase Sprint 10 | 0.38462 | 0.21875 | Mortgage Purchase Sprint 10 | 0.38462 | 0.125
[23 empty] | Mortgage Purchase Sprint 11 | 0.41176 | 0.34783 | Mortgage Purchase Sprint 11 | 0.17647 | 0.43478
[23 empty] | Mortgage Purchase Sprint 12 | 0 | 0.2 | Mortgage Purchase Sprint 12 | 0 | 0.16667
[23 empty] | Mortgage Purchase Sprint 13 | 0.17647 | 0.19048 | Mortgage Purchase Sprint 13 | 0 | 0
[23 empty] | Mortgage Purchase Sprint 14 | 0.16667 | 0.11765 | Mortgage Purchase Sprint 14 | 0.25 | 0
[23 empty] | Grand Total | 1.3703 | 1.9209 | Grand Total | 1.3111 | 1.2136
[23 empty] | Sprint | V2 | LT | Sprint | V2 | LT
[23 empty] | Row Labels | Sum of Planned Vs Completed ratio
[23 empty] | Mortgage Purchase Sprint 8 | 0.63265
[23 empty] | Mortgage Purchase Sprint 9 | 0.88462
[23 empty] | Mortgage Purchase Sprint 10 | 0.8
[23 empty] | Mortgage Purchase Sprint 11 | 0.675
[23 empty] | Mortgage Purchase Sprint 12 | 0.86111
[23 empty] | Mortgage Purchase Sprint 13 | 1
[23 empty] | Mortgage Purchase Sprint 14 | 0.89655
[23 empty] | Grand Total | 5.7499
[23 empty] | Sprint | Planned Vs Completed Ratio
Note on T1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sprint name
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points planned during sprint planning.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points moved to PD.
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by V2 resources.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by LT resources.
Note on Y1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for V2 resources.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for LT resources.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for V2 resources.
Note on AB1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for LT resources.
Note on AC1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered by V2 resources - Total number of story points re-opened.
Note on AD1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by V2 resources over Total number of story points re-opened.
Note on AE1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by LT resources over Total number of story points re-opened.
Note on AF1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by V2resources over Total number of story points carry-over.
Note on AG1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by LT resources over Total number of story points carry-over.
Note on AF3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Blocked due to DB task
Note on AF8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Blocked due to DB task

## CDR (hidden)
[8 empty] | Week Starting On | Planned Story points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio
PROJECT HEALTH DASHBOARD | [7 empty] | CDR 6/02 - 6/16 | 19 | 0 | 8 | 11 | 0 | 0 | 8 | 11 | 0 |  | 0% | 0% | 0% | 0%
[8 empty] | CDR 6/16 - 6/30 | 22 | 19 | 11 | 11 | 0 | 0 | 2 | 0 | 19
[8 empty] | CDR 6/30 - 7/14 | 21 | 16 | 11 | 10 | 0 | 3 | 5 | 0 | 16
[8 empty] | CDR 7/15 - 7/28 | 24 | 0 | 18 | 6 | 11 | 3 | 18 | 6 | 0
| Project Name | LendingTree |  |  |  | Status Date | 27/12/2021 | CDR 7/28 - 8/11 | 29 | 18 | 13 | 5 | 0 | 3 | 13 | 8 | 18
| Sub Project | Consumer Distributed Retail | [5 empty] | CDR 8/11 - 8/25 | 29 | 21 | 13 | 16 | 0 | 3 | 0 | 8 | 21
| Delivery Manager | Mamatha |  |  |  | Overall Status | Green | CDR 8/25 - 9/08 | 18 | 16 | 5 | 15 | 0 | 2 | 0 | 5 | 0
| Project Manager/Lead | Saurabh | [5 empty] | CDR 9/08 - 9/22 | 15 | 15 | 9 | 6 | 0 | 2 | 0 | 6 | 15
| Client POC | - | [5 empty] | CDR 9/22 - 10/06 | 19 | 18 | 5 | 26 | 0 | 0 | 3 | 10 | 18
| Client Feedback | - | [5 empty] | CDR 10/06 - 10/20 | 19 | 18 | 5 | 26 | 0 | 0 | 3 | 10 | 18
| Team Allocation | [6 empty] | CDR 10/20 - 11/01 | 19 | 18 | 5 | 26 | 0 | 0 | 3 | 10 | 18
| Off-shore team | Allocated | 1 | Billable | 1 |  |  | CDR 11/03 - 11/17 | 30 | 30 | 12 | 18 | 2 | 0 | 0 | 0 | 30
| On-site team | Allocated | [5 empty] | CDR 11/17 - 12/01 | 14 | 14 | 3 | 11 | 0 | 0 | 0 | 0 | 14
[8 empty] | CDR 12/01 - 12/15 | 15 | 16 | 9 | 7 | 0 | 3 | 0 | 0 | 16
[8 empty] | CDR 12/15 - 12/29 | 21 | 7 | 3 | 4 | 0 | 0 | 6 | 8 | 18
[8 empty] | CDR 12/29 - 12/01 |  |  |  | 7 | 0 | 3 | 0 | 0 | 16
Note on S1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sprint name
Note on T1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points planned during sprint planning.
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points moved to PD.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by V2 resources.
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by LT resources.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for V2 resources.
Note on Y1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for LT resources.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for V2 resources.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for LT resources.
Note on AB1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered by V2 resources - Total number of story points re-opened.
Note on AC1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by V2 resources Over Total number of story points re-opened.
Note on AD1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by LT resources over Total number of story points re-opened.
Note on AE1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by V2 resources over Total number of story points carry-over.
Note on AF1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by LT resources over Total number of story points carry-over.
Note on U2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Due to dependency on DB schema and store procedures.
Note on AE2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Waiting for DB schema and storeproc changes
Note on AF2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Waiting for DB schema and storeproc changes
Note on AG2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Waiting for DB schema and storeproc changes
Note on Z4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scope Change CDR-49 was excluded
Note on AE4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scope Change CDR-49 was excluded
Note on AG4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scope Change CDR-49 was excluded
Note on U5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Due to dependency on funding API and canopy API our tickets got delayed..
Note on AC5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CDR-16 AND CDR-46 was block because of funding API issue CDR-36 and CDR-79 was added new scope to current sprint CDR-38 and CDR-39 was waiting for UAT
Note on AD5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CDR-16 AND CDR-46 was block because of funding API issue CDR-36 and CDR-79 was added new scope to current sprint CDR-38 and CDR-39 was waiting for UAT
Note on AE5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CDR-16 AND CDR-46 was block because of funding API issue CDR-36 and CDR-79 was added new scope to current sprint CDR-38 and CDR-39 was waiting for UAT
Note on AF5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CDR-16 AND CDR-46 was block because of funding API issue CDR-36 and CDR-79 was added new scope to current sprint CDR-38 and CDR-39 was waiting for UAT
Note on AG5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CDR-16 AND CDR-46 was block because of funding API issue CDR-36 and CDR-79 was added new scope to current sprint CDR-38 and CDR-39 was waiting for UAT
Note on U6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Due to dependency on funding API and canopy API our tickets got delayed..
Note on AE16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1. CDR-204 - Got carryforward as UAT was not available because of leave 2. CDR-216 - Waiting for SP (CDR-231) changes as DB was not available because of leave

## SnapCap (hidden)
[8 empty] | Week Starting On | Planned Story Points | Actaul Delivered | V2 | LT | Rework V2 | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio | Row Labels | Sum of V2 | Sum of LT | Row Labels | Sum of QA Passed
PROJECT HEALTH DASHBOARD | [7 empty] | 2020: SC 4.1 |  | 46 | 13 | 33 | 2 | 12 | 2 | 0 | [6 empty] | 1 |  |  | 2021: SC 8.2 | 0 |  | Green
[8 empty] | 2020: SC 4.2 |  | 34 | 12 | 22 | 8 | 1 | 0 | 5 | [6 empty] | 2 |  |  | 2021: SC 9.1 | 10 |  | Red
[8 empty] | 2020: SC 5.1 |  | 51 | 17 | 34 | 6 | 11 | 0 | 9 | [6 empty] | 3 |  |  | 2021: SC 9.2 | 9 |  | Amber
[8 empty] | 2020: SC 5.2 |  | 43 | 17 | 26 | 9 | 9 | 9 | 0 | [6 empty] | 5 |  |  | 2021: SC 9.3 | 9
| Project Name | LendingTree |  |  |  | Status Date | 2022-05-03 | 2020: SC 6.1 |  | 29 | 14 | 15 | 15 | 7 | 3 | 0 | [9 empty] | 2021: SC 10.1 | 6
| Sub Project | Snapcap | [5 empty] | 2020: SC 6.2 |  | 52 | 11 | 41 | 3 | 15 | 0 | 3 | [9 empty] | 2021: SC 10.2 | 13
| Delivery Manager | Mamatha |  |  |  | Overall Status | Green | 2020: SC 7.1 |  | 44 | 12 | 32 | 3 | 12 | 6 | 0 | [9 empty] | Grand Total | 47
| Project Manager/Lead | Jayant | [5 empty] | 2020: SC 7.2 |  | 54 | 10 | 44 | 5 | 9 | 0 | 0
| Client POC | - | [5 empty] | 2020: SC 7.3 |  | 30 | 9 |  | 5 | 15 | 0 | 6
| Client Feedback | - | [5 empty] | 2020: SC 8.1 |  | 49 | 17 |  | 6 | 14 | 0 | 5
| Team Allocation | [6 empty] | 2020: SC 8.2 |  | 55 | 32 |  | 11 | 11 | 1 | 3 | [6 empty] | Sprint | V2 (1 dev) | LT (2 dev) | QA Passed
| Off-shore team | Allocated | 1 | Billable | 1 |  |  | 2020: SC 9.1 |  | 58 | 34 |  | 10 | 20 | 0 | 3 | [9 empty] | Rework
| On-site team | Allocated billable | [5 empty] | 2020: SC 9.2 |  | 53 | 14 | 36 | 5 | 10 | 3 | 10
[8 empty] | 2020: SC 10.1 |  | 33 | 7 | 25 | 7 | 9 | 3 | 3
[8 empty] | 2020: SC 10.2 |  | 23 | 10 | 12 | 11 | 11 | 3 | 10
[8 empty] | 2020: SC 11.1 | 28 | 28 | 7 | 21 | 0 | 11 | 2 | 2 | [9 empty] | Row Labels | Sum of Planned Vs Completed ratio
[8 empty] | 2020: SC 11.2 | 27 | 26 | 0 | 26 | 2 | 9 | 5 | 0 |  | 0% |  | 0% | [5 empty] | 2021: SC 8.2 | 0.85714
[8 empty] | 2020: SC 12.1 | 26 | 32 | 10 | 19 | 7 | 10 | 0 | 8 | [9 empty] | 2021: SC 9.1 | 1.4
[8 empty] | 2020: SC 12.2 | 26 | 22 | 2 | 20 | 0 | 7 | 0 | 8 | [9 empty] | 2021: SC 9.2 | 1.3333
[8 empty] | 2021: SC 1.1 | 21 | 21 | 8 | 13 | 8 | 10 | 0 | 3 | [9 empty] | 2021: SC 9.3 | 1
[8 empty] | 2021: SC 1.2 | 18 | 22 | 8 | 14 | 7 | 8 | 2 | 6 | [9 empty] | 2021: SC 10.1 | 1.0357
[8 empty] | 2021: SC 2.1 | 27 | 28 | 10 | 18 | 2 | 3 | 1 | 3 | [9 empty] | 2021: SC 10.2 | 1.069
[8 empty] | 2021: SC 3.1 | 30 | 34 | 10 | 24 | 5 | 3 | 2 | 2 | [9 empty] | Grand Total | 6.6952
[8 empty] | 2021: SC 3.2 | 27 | 42 | 11 | 31 | 1 | 7 | 0 | 2
[8 empty] | 2021: SC 4.1 | 26 | 30 | 8 | 22 | 0 | 7 | 0 | 4
[8 empty] | 2021: SC 4.2 | 33 | 36 | 16 | 21 | 5 | 8 | 0 | 2 | [9 empty] | Sprint | Planned Vs Completed ratio
[8 empty] | 2021: SC 5.1 | 31 | 36 | 8 | 28 | 2 | 0 | 0 | 0
[8 empty] | 2021: SC 5.2 | 27 | 27 | 9 | 18 | 0 | 5 | 0 | 0
[8 empty] | 2021: SC 6.1 | 36 | 24 | 8 | 16 | 0 | 10 | 5 | 7
[8 empty] | 2021: SC 6.2 | 31 | 29 | 9 | 20 | 5 | 2 | 0 | 2
[8 empty] | 2021: SC 7.1 | 25 | 19 | 9 | 10 | 0 | 8 | 0 | 6
[8 empty] | 2021: SC 7.2 | 24 | 21 | 8 | 13 | 0 | 5 | 0 | 3
[8 empty] | 2021: SC 8.1 | 21 | 21 | 7 | 14 | 0 | 5 | 0 | 0
[8 empty] | 2021: SC 8.2 | 21 | 18 | 3 | 15 | 3 | 15 | 0 | 3
[8 empty] | 2021: SC 9.1 | 15 | 21 | 10 | 11 | 0 | 8 | 0 | 4
[8 empty] | 2021: SC 9.2 | 21 | 28 | 9 | 19 | 0 | 2 | 0 | 0
[8 empty] | 2021: SC 9.3 | 22 | 22 | 12 | 10 | 3 | 2 | 0 | 0
[8 empty] | 2021: SC 10.1 | 28 | 29 | 12 | 17 | 6 | 5 | 0 | 0
[8 empty] | 2021: SC 10.2 | 29 | 31 | 15 | 16 | 2 | 3 | 0 | 3
[23 empty] | Row Labels | Sum of V2 Reopen Percentage | Sum of LT Reopen Percentage
[23 empty] | 2021: SC 8.2 | 1 | 1
[8 empty] | 2020: SC 11.2 | Sachin had assigned 5 story points | [13 empty] | 2021: SC 9.1 | 0 | 0.72727
[8 empty] | 2021: SC 3.1 | Additional Story Point: 2 Carry Forward: Issue from Equifax API which is not assign to sachin Reopen: Issue in subtask which is not assign to sachin | [13 empty] | 2021: SC 9.2 | 0 | 0.10526
[8 empty] | 2021: SC 3.2 | Reopen: Requirment change | [13 empty] | 2021: SC 9.3 | 0.25 | 0.2
[8 empty] | 2021: SC 4.2 | SNAP-2938 - Reopen due to mock up not provided | [13 empty] | 2021: SC 10.1 | 0.5 | 0.29412
[8 empty] | 2021: SC 5.1 | Not an issue - LT - Added new file and forget to merge with new changes. This issue need's to be fixed from Devops team. (Global Issue) | [13 empty] | 2021: SC 10.2 | 0.13333 | 0.1875 | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[8 empty] | 2021: SC 6.2 | SNAP-3087: One issue wasn't related and task is moved out from the this story ticket. SNAP-3069: Change request. | [16 empty] | 2021: SC 8.2 | 0 | 0.2
[8 empty] | 2021: SC 8.2 | SNAP-3156 - SNAP-3252 - Redirect Page ¦ Account Details Form ¦ UI Discrepancy | [16 empty] | 2021: SC 9.1 | 0 | 0.36364
[8 empty] | 2021: SC 9.3 | SNAP-3317 : SNAP-3336 - Phoneix updated industry names (Change Request - No one update to us) | [16 empty] | 2021: SC 9.2 | 0 | 0
[8 empty] | 1 | [14 empty] | Sprint | V2 (1 dev) | LT (2 dev) | 2021: SC 9.3 | 0 | 0
[8 empty] | 2 | [17 empty] | 2021: SC 10.1 | 0 | 0
[8 empty] | 3 | [17 empty] | 2021: SC 10.2 | 0 | 0.1875
5
[26 empty] | Sprint | V2 (1 dev) | LT (2 dev)
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points planned during sprint planning.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points moved to PD.
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by V2 resources.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by LT resources.
Note on Y1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for V2 resources.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for LT resources.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for V2 resources.
Note on AB1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for LT resources.
Note on AC1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered by V2 resources - Total number of story points re-opened.
Note on V22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4 tickets added after sprint started. 2698, 2712 are two tickets which had 2 story points each. Rest of the tickets were 0 story points.
Note on V23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Bug SNAP-2781 is added later in Sprint which had 1 story point
Note on V24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2842, 2860, 2867 added later in the sprint.
Note on AA24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SNAP-2532: Blocked due to issue in equifax api
Note on V25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Several bugs, story tickets added sprint later. I dont remember now why we did that. It could dev might have finished the work on some tickets out of the sprint.
Note on Y25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SNAP-2721 : Reopened due to change request
Note on V26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2962, 2964, 2968 are added later to sprint because Dev have capacity to complete more work.
Note on V27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2987, 2996 added later because dev has capacity to do more work.
Note on V28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Two Prod bugs and one story ticket is added later
Note on AA30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tickets were blocked due to no response from the Lender on issues faced during the development.
Note on AB30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Two tickets were blocked due to dependency on another projects. One ticket has bug and reopened on last day.
Note on Y31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SNAP-3087: One issue wasn't code related and another sub task is moved out from the this story ticket. SNAP-3069: Change request.
Note on AB31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SNAP-2541: Blocked due to delay in response from Experian credit pull service customer care.
Note on Y38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SNAP-3317 : SNAP-3336 - Phoneix updated industry names (Change Request - No one update to us)

## LONB (hidden)
[8 empty] | Week Starting On | Planned Story points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio | Row Labels | Sum of V2 | Sum of LT | Row Labels | Sum of Rework | Sum of QA Passed
PROJECT HEALTH DASHBOARD | [7 empty] | LONB 3/31- 4/14 |  |  | 24 | 0 | 18 | 0 | 0 | 0 | [6 empty] | LONB 5/25 - 6/08 | 35 | 7 | LONB 5/25 - 6/08 | 12 | 23
[8 empty] | LONB 4/14 - 4/28 |  | 32 | 32 | 0 | 14 | 0 | 4 | 0 | [6 empty] | LONB 6/08 - 6/22 | 27 | 23 | LONB 6/08 - 6/22 | 8 | 19
[8 empty] | LONB 4/28 - 5/12 |  | 32 | 32 | 0 | 5 | 0 | 0 | 0 | [6 empty] | LONB 6/22 - 7/06 | 21 | 34 | LONB 6/22 - 7/06 | 3 | 18
[8 empty] | LONB 5/12 - 5/26 |  | 14 | 14 | 0 | 10 | 0 | 10 | 5 | [6 empty] | LONB 7/06 - 7/20 | 26 | 25 | LONB 7/06 - 7/20 | 11 | 15
| Project Name | LendingTree |  |  |  | Status Date | 2022-01-04 | LONB 5/26 - 6/9 |  | 25 | 25 | 0 | 5 | 0 | 1 | 0 | [6 empty] | LONB 7/20 - 8/03 | 38 | 15 | LONB 7/20 - 8/03 | 8 | 30
| Sub Project | Lender Onboarding | [5 empty] | LONB 6/9 - 6/23 |  | 30 | 30 | 0 | 6 | 0 | 0 | 0 | [6 empty] | LONB 8/03 - 8/17 | 23 | 46 | LONB 8/03 - 8/17 | 5 | 18
| Delivery Manager | Rajneesh |  |  |  | Overall Status | Green | LONB 6/23 - 7/7 |  | 18 | 18 | 2 | 6 | 0 | 0 | 4 | [6 empty] | LONB 8/017 - 8/31 | 17 | 14 | LONB 8/017 - 8/31 | 0 | 17
| Project Manager/Lead | Saurabh | [5 empty] | LONB 7/7 - 7/21 |  | 26 | 22 | 4 | 0 | 0 | 8 | 0 | [6 empty] | Grand Total | 187 | 164 | Grand Total | 47 | 140
| Client POC | - | [5 empty] | LONB 7/21 - 8/4 |  | 30 | 26 | 4 | 2 | 4 | 2 | 4
| Client Feedback | - | [5 empty] | LONB 8/4 - 8/18 |  | 26 | 16 | 10 | 2 | 5 | 0 | 3
| Team Allocation | [6 empty] | LONB 8/18 - 9/1 |  | 15 | 12 | 3 | 2 | 7 | 4 | 0 | [6 empty] | Sprint | V2 | LT | QA Passed
| Off-shore team | Allocated | 1 | Billable | 1 |  |  | LONB 9/1 - 9/15 |  | 27 | 27 | 0 | 5 | 2 | 3 | 0 | [9 empty] | Rework
| On-site team | Allocated | [5 empty] | LONB 9/15 - 9/29 |  | 32 | 26 | 6 | 4 | 0 | 0 | 0
[8 empty] | LONB 9/29 - 10/13 |  | 31 | 19 | 12 | 0 | 0 | 2 | 0
[8 empty] | LONB 10/13 - 10/27 |  | 35 | 19 | 11 | 3 | 7 | 3 | 14
[8 empty] | LONB 10/27 - 11/11 | 34 | 52 | 33 | 19 | 5 | 5 | 0 | 0
[8 empty] | LONB 11/11 - 11/24 | 35 | 19 | 10 | 9 | 5 | 2 | 18 | 5
[8 empty] | LONB 11/24 - 12/8 | 24 | 23 | 20 | 3 | 1 | 0 | 1 | 0
[8 empty] | LONB 12/8 - 12/22 | 26 | 26 | 21 | 5 | 0 | 3 | 0 | 0
[8 empty] | LONB 12/2 - 1/5 | 18 | 18 | 16 | 2 | 10 | 0 | 0 | 0
[8 empty] | LONB 1/5 - 1/19 | 31 | 31 | 24 | 7 | 0 | 2 | 0 | 0 | [6 empty] | Row Labels | Sum of V2 Reopen Percentage | Sum of LT Reopen Percentage | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[8 empty] | LONB 1/19 - 2/2 | 37 | 30 | 23 | 7 | 5 | 3 | 4 | 3 | [6 empty] | LONB 5/25 - 6/08 | 0.34286 | 0 | LONB 5/25 - 6/08 | 0.46667 | 0.066667
[8 empty] | LONB 2/2 - 2/16 | 32 | 32 | 24 | 8 | 4 | 0 | 0 | 0 | [6 empty] | LONB 6/08 - 6/22 | 0.2963 | 0.275 | LONB 6/08 - 6/22 | 0.125 | 0.125
[8 empty] | LONB 2/16 - 3/2 | 47 | 34 | 19 | 15 | 7 | 2 | 10 | 3 | [6 empty] | LONB 6/22 - 7/06 | 0.14286 | 0.28205 | LONB 6/22 - 7/06 | 0.10256 | 0.30769
[8 empty] | LONB 3/2 - 3/16 |  | 76 | 35 | 11 | 9 | 0 | 0 | 0 | [6 empty] | LONB 7/06 - 7/20 | 0.42308 | 0.77778 | LONB 7/06 - 7/20 | 0.61111 | 0.66667
[8 empty] | LONB 3/16- 3/30 |  | 53 | 40 | 13 | 4 | 3 | 5 | 0 | [6 empty] | LONB 7/20 - 8/03 | 0.21053 | 0.2 | LONB 7/20 - 8/03 | 0.24444 | 0.13333
[8 empty] | LONB 3/30- 4/13 | 50 |  | 35 | 15 | 4 | 0 | 2 | 9 | [6 empty] | LONB 8/03 - 8/17 | 0.21739 | 0.10714 | LONB 8/03 - 8/17 | 0.39286 | 0.57143
[8 empty] | LONB 4/13 - 4/27 | 45 |  | 28 | 17 | 7 | 2 | 15 | 7 | [6 empty] | LONB 8/017 - 8/31 | 0 | 0 | LONB 8/017 - 8/31 | 0 | 0.086957
[8 empty] | LONB 4/27 - 5/11 | 47 |  | 37 | 10 | 10 | 0 | 10 | 3 | [6 empty] | Grand Total | 1.633 | 1.642 | Grand Total | 1.9426 | 1.9577
[8 empty] | LONB 5/11 - 5/25 | 45 |  | 34 | 11 | 14 | 2 | 15 | 5
[8 empty] | LONB 5/25 - 6/08 | 46 |  | 35 | 7 | 12 | 0 | 14 | 2 | [6 empty] | Sprint | V2 | LT | Sprint | V2 | LT
[8 empty] | LONB 6/08 - 6/22 | 50 |  | 27 | 23 | 8 | 11 | 5 | 5
[8 empty] | LONB 6/22 - 7/06 | 55 |  | 21 | 34 | 3 | 11 | 4 | 12
[8 empty] | LONB 7/06 - 7/20 | 32 | 18 | 26 | 25 | 11 | 14 | 11 | 12
[8 empty] | LONB 7/20 - 8/03 | 34 | 45 | 38 | 15 | 8 | 9 | 11 | 6
[8 empty] | LONB 8/03 - 8/17 | 35 | 28 | 23 | 46 | 5 | 3 | 11 | 16
[8 empty] | LONB 8/017 - 8/31 | 40 | 23 | 17 | 14 | 0 | 0 | 0 | 2
[23 empty] | Row Labels | Sum of Planned Vs Completed ratio
[23 empty] | LONB 5/25 - 6/08 | 1.1667
[23 empty] | LONB 6/08 - 6/22 | 0.675
[23 empty] | LONB 6/22 - 7/06 | 1.1667
[23 empty] | LONB 7/06 - 7/20 | 1.4444
[23 empty] | LONB 7/20 - 8/03 | 0.84444
[23 empty] | LONB 8/03 - 8/17 | 0.82143
[23 empty] | LONB 8/017 - 8/31 | 0.73913
[23 empty] | Grand Total | 6.8578
[23 empty] | Sprint | Sum of Planned Vs Completed Ratio
Note on S1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sprint name
Note on T1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points planned during sprint planning.
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points moved to PD.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by V2 resources.
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by LT resources.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for V2 resources.
Note on Y1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for LT resources.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for V2 resources.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for LT resources.
Note on AB1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered by V2 resources - Total number of story points re-opened.
Note on AC1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by V2 resources Over Total number of story points re-opened.
Note on AD1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by LT resources over Total number of story points re-opened.
Note on AE1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by V2 resources over Total number of story points carry-over.
Note on AF1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by LT resources over Total number of story points carry-over.
Note on AC25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Multiple dependent ticket for Good Faith Credit (LONB-1562 epic) New developer getting upto the speed.
Note on AC26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Multiple dependent ticket for Good Faith Credit (LONB-1562 epic)
Note on AC30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .Net core framework upgrade from 2.2 to 3.1 in UI and API Dependency with the OTA team for pipeline changes with .net upgrade changes
Note on AC31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: LONB-1863 - merging issue on stage LONB-1769 - Scope Change LONB-1771 - Reopened by Hanuman, as tester don't have bandwidth to test and got moved to next sprint to test
Note on AE31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9 story points is in UAT, for which doesn't have enough bandwidth to verify 3 story points is Testing even after 3 days 5 points are in dev complete as tester doesn't have enough bandwidth to test so kept in dev complete
Note on AE33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As per discussion in scrum, developer were ask to keep below ticket in dev complete and to not to move to testing since testing team does not have bandwidth to test. LONB-1720, LONB-1721, LONB-1722, LONB-1723, LONB-1724
Note on AG33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As per discussion in scrum, developer were ask to keep below ticket in dev complete and to not to move to testing since testing team does not have bandwidth to test. LONB-1720, LONB-1721, LONB-1722, LONB-1723, LONB-1724

## Voltron (hidden)
Week Starting On | Planned Story Points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Old Dates | Row Labels | Sum of V2 | Sum of LT | Row Labels | Sum of Rework | Sum of QA Passed
LCS: 4/06 - 4/13 |  | 28 | 28 | 0 | 8 | 0 | 0 | 0 |  |  | 0% |  | 0% | 2020-04-06 | LCS: 6/29 - 7/06 | 3 | 7 | LCS: 6/29 - 7/06 | 0 | 3
LCS: 4/13 - 4/20 |  | 21 | 18 | 3 | 5 | 0 | 0 | 0 | [5 empty] | 2020-04-13 | LCS: 7/06 - 7/13 | 24 | 6 | LCS: 7/06 - 7/13 | 0 | 24
LCS: 4/20 - 4/27 |  | 35 | 24 | 11 | 3 | 3 | 0 | 0 | [5 empty] | 2020-04-20 | LCS: 7/13 - 7/20 | 27 | 3 | LCS: 7/13 - 7/20 | 0 | 27
LCS: 4/27 - 5/04 |  | 19 | 11 | 8 | 0 | 0 | 0 | 0 | [5 empty] | 2020-04-27 | LCS: 7/20 - 7/27 | 24 | 2 | LCS: 7/20 - 7/27 | 0 | 24
LCS: 5/04 - 5/11 |  | 19 | 9 | 10 | 0 | 13 | 0 | 0 | [5 empty] | 2020-05-04 | LCS: 7/27 - 8/03 | 8 | 1 | LCS: 7/27 - 8/03 | 0 | 8
LCS: 5/11 - 5/18 |  | 25 | 17 | 8 | 3 | 0 | 0 | 0 | [5 empty] | 2020-05-11 | LCS: 8/03 - 8/10 | 18 | 2 | LCS: 8/03 - 8/10 | 0 | 18
LCS: 5/18 - 5/25 |  | 45 | 32 | 13 | 3 | 0 | 0 | 0 | [5 empty] | 2020-05-18 | LCS: 8/10 - 8/17 | 24 | 3 | LCS: 8/10 - 8/17 | 0 | 24
LCS: 5/25 - 6/01 |  | 10 | 10 | 0 | 0 | 3 | 0 | 0 |  |  | 0% |  | 0% | 2020-05-25 | LCS: 8/17 - 8/24 | 9 | 1 | LCS: 8/17 - 8/24 | 0 | 9
LCS: 6/01 - 6/08 |  | 28 | 20 | 8 | 0 | 6 | 0 | 0 | [5 empty] | 2020-06-01 | LCS: 8/24 - 8/31 | 20 | 0 | LCS: 8/24 - 8/31 | 3 | 17
LCS: 6/08 - 6/15 |  | 35 | 26 | 9 | 0 | 0 | 0 | 0 | [5 empty] | 2020-06-08 | LCS: 9/07 - 9/14 | 21 | 1 | LCS: 9/07 - 9/14 | 2 | 19
LCS: 6/15 - 6/22 |  | 12 | 6 | 6 | 3 | 0 | 0 | 0 | [5 empty] | 2020-06-15 | LCS: 9/14 - 9/21 | 16 | 3 | LCS: 9/14 - 9/21 | 2 | 14
LCS: 6/22 - 6/29 |  | 18 | 18 | 0 | 0 | 2 | 0 | 0 |  |  | 0% |  | 0% | 2020-06-22 | LCS: 9/21 - 9/28 | 17 | 0 | LCS: 9/21 - 9/28 | 4 | 13
LCS: 6/29 - 7/06 |  | 10 | 3 | 7 | 0 | 2 | 0 | 0 | [5 empty] | 2020-06-29 | LCS: 9/28 - 10/05 | 15 | 5 | LCS: 9/28 - 10/05 | 0 | 15
LCS: 7/06 - 7/13 |  | 30 | 24 | 6 | 0 | 0 | 0 | 0 | [5 empty] | 2020-07-06 | LCS: 8/31 - 9/07 | 13 | 7 | LCS: 8/31 - 9/07 | 3 | 10
LCS: 7/13 - 7/20 |  | 30 | 27 | 3 | 0 | 2 | 0 | 0 | [5 empty] | 2020-07-13 | Grand Total | 239 | 41 | Grand Total | 14 | 225
LCS: 7/20 - 7/27 |  | 26 | 24 | 2 | 0 | 0 | 0 | 0 | [5 empty] | 2020-07-20
LCS: 7/27 - 8/03 |  | 9 | 8 | 1 | 0 | 2 | 0 | 0 | [5 empty] | 2020-07-27
LCS: 8/03 - 8/10 |  | 20 | 18 | 2 | 0 | 1 | 0 | 0 | [5 empty] | 2020-08-03 | Kanban Week | V2 | LT | QA Passed
LCS: 8/10 - 8/17 |  | 27 | 24 | 3 | 0 | 0 | 0 | 0 | [5 empty] | 2020-08-10 |  |  |  | Rework
LCS: 8/17 - 8/24 |  | 10 | 9 | 1 | 0 | 0 | 0 | 0 | [5 empty] | 2020-08-17
LCS: 8/24 - 8/31 |  | 20 | 20 | 0 | 3 | 3 | 0 | 0 |  |  | 0% |  | 0% | 2020-08-24
LCS: 8/31 - 9/07 |  | 20 | 13 | 7 | 3 | 3 | 0 | 0 | [5 empty] | 2020-08-31
LCS: 9/07 - 9/14 |  | 22 | 21 | 1 | 2 | 2 | 0 | 0 | [5 empty] | 2020-09-07
LCS: 9/14 - 9/21 |  | 19 | 16 | 3 | 2 | 2 | 0 | 0 | [5 empty] | 2020-09-14
LCS: 9/21 - 9/28 |  | 17 | 17 | 0 | 4 | 0 | 0 | 0 |  |  | 0% |  | 0% | 2020-09-21
LCS: 9/28 - 10/05 |  | 20 | 15 | 5 | 0 | 0 | 0 | 0 | [5 empty] | 2020-09-28
[15 empty] | Row Labels | Sum of V2 Reopen Percentage | Sum of LT Reopen Percentage | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[15 empty] | LCS: 6/29 - 7/06 | 0 | 0.28571 | LCS: 6/29 - 7/06 | 0 | 0
[15 empty] | LCS: 7/06 - 7/13 | 0 | 0 | LCS: 7/06 - 7/13 | 0 | 0
[15 empty] | LCS: 7/13 - 7/20 | 0 | 0.66667 | LCS: 7/13 - 7/20 | 0 | 0
[15 empty] | LCS: 7/20 - 7/27 | 0 | 0 | LCS: 7/20 - 7/27 | 0 | 0
[15 empty] | LCS: 7/27 - 8/03 | 0 | 2 | LCS: 7/27 - 8/03 | 0 | 0
[15 empty] | LCS: 8/03 - 8/10 | 0 | 0.5 | LCS: 8/03 - 8/10 | 0 | 0
[15 empty] | LCS: 8/10 - 8/17 | 0 | 0 | LCS: 8/10 - 8/17 | 0 | 0
[15 empty] | LCS: 8/17 - 8/24 | 0 | 0 | LCS: 8/17 - 8/24 | 0 | 0
[15 empty] | LCS: 8/24 - 8/31 | 0.15 | 0 | LCS: 8/24 - 8/31 | 0 | 0
[15 empty] | LCS: 9/07 - 9/14 | 0.095238 | 2 | LCS: 9/07 - 9/14 | 0 | 0
[15 empty] | LCS: 9/14 - 9/21 | 0.125 | 0.66667 | LCS: 9/14 - 9/21 | 0 | 0
[15 empty] | LCS: 9/21 - 9/28 | 0.23529 | 0 | LCS: 9/21 - 9/28 | 0 | 0
[15 empty] | LCS: 9/28 - 10/05 | 0 | 0 | LCS: 9/28 - 10/05 | 0 | 0
[15 empty] | LCS: 8/31 - 9/07 | 0.23077 | 0.42857 | LCS: 8/31 - 9/07 | 0 | 0
[15 empty] | Grand Total | 0.8363 | 6.5476 | Grand Total | 0 | 0
[15 empty] | Sprint | V2 | LT | Sprint | V2 | LT

## MyLT DASH (hidden)
[8 empty] | Week Starting On | Planned Story Points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio | Row Labels | Sum of V2 | Sum of LT | Row Labels | Sum of Rework | Sum of QA Passed
PROJECT HEALTH DASHBOARD | [7 empty] | DASH 4/07-4/21 | 77 | 49 | 13 |  | 2 | 25 | 0 | 0 | [6 empty] | DASH 7/28-8/11 | 6 | 92 | DASH 7/28-8/11 | 6 | 0 | Green
[8 empty] | DASH 4/21-5/05 | 92 | 67 | 7 |  | 2 | 22 | 3 | 17 | [6 empty] | DASH 8/11-8/25 | 13 | 65 | DASH 8/11-8/25 | 10 | 8 | Red
[8 empty] | DASH 5/05-5/19 | 70 | 67 | 11 |  | 5 | 9 | 0 | 3 | [6 empty] | DASH 8/25-9/08 | 9 | 65 | DASH 8/25-9/08 | 5 | 4 | Amber
[8 empty] | DASH 5/19-6/02 | 80 | 49 | 10 |  | 0 | 13 | 5 | 26 | [6 empty] | DASH 9/22-10/06 | 7 | 69 | DASH 9/22-10/06 | 3 | 4
| Project Name | LendingTree |  |  |  | Status Date | 2021-12-27 | DASH 6/02-6/16 | 96 | 77 | 10 |  | 10 | 17 | 0 | 17 | [6 empty] | DASH 10/06-10/20 | 9 | 85 | DASH 10/06-10/20 | 2 | 6
| Sub Project | MyLT Dash | [5 empty] | DASH 6/16-6/30 | 82 | 54 | 5 |  | 0 | 6 | 5 | 17 | [6 empty] | DASH 10/20-11/03 | 6 | 59 | DASH 10/20-11/03 | 3 | 3
| Delivery Manager | Mamatha |  |  |  | Overall Status | Green | DASH 6/30-7/14 | 82 | 56 | 9 |  | 0 | 12 | 0 | 24 | [9 empty] | Grand Total | 29 | 25
| Project Manager/Lead | Ramesh | [5 empty] | DASH 7/14-7/28 | 84 | 70 | 2 |  | 0 | 13 | 0 | 11
| Client POC | - | [5 empty] | DASH 7/28-8/11 | 98 | 81 | 6 |  | 6 | 24 | 6 | 49
| Client Feedback | - | [5 empty] | DASH 8/11-8/25 | 78 | 70 | 13 |  | 10 | 46 | 5 | 3
| Team Allocation | [6 empty] | DASH 8/25-9/08 | 74 |  | 9 |  | 5 | 10 | 5 | 17 | [6 empty] | Sprint | V2 | LT | QA Passed
| Off-shore team | Allocated | 1 | Billable | 1 |  |  | DASH 9/22-10/06 | 76 | 62 | 7 |  | 3 | 5 | 3 | 10 | [9 empty] | Rework
| On-site team | Allocated | [5 empty] | DASH 10/06-10/20 | 94 | 44 | 9 |  | 2 | 6 | 3 | 12
[8 empty] | DASH 10/20-11/03 | 65 | 72 | 6 |  | 3 | 6 | 3 | 11
[8 empty] | DASH 11/03-11/17 | 55 | 60 | 0 |  | 0 | 10 | 0 | 8
[8 empty] | DASH 11/17-12/01 | 45 | 25 | 2 |  | 0 | 9 | 0 | 17
[23 empty] | PRO 7/27-8/10 | 9 | 45
[23 empty] | Rework Trend Analysis (V2 vs LT) |  |  | Carryover Trend Analysis (V2 vs LT)
[23 empty] | Row Labels | Sum of V2 Reopen Percentage | Sum of LT Reopen Percentage | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[23 empty] | DASH 7/28-8/11 | 1 | 0.26087 | Grand Total
[23 empty] | DASH 8/11-8/25 | 0.76923 | 0.70769
[23 empty] | DASH 8/25-9/08 | 0.55556 | 0.15385
[23 empty] | DASH 9/22-10/06 | 0.42857 | 0.072464
[23 empty] | DASH 10/06-10/20 | 0.22222 | 0.070588
[23 empty] | DASH 10/20-11/03 | 0.5 | 0.10169
[23 empty] | Grand Total | 3.4756 | 1.3672
[23 empty] | Sprint | V2 | LT | Sprint | V2 | LT
[23 empty] | Row Labels | Sum of Planned Vs Completed ratio
Grand Total
[23 empty] | Sprint | Sum of Planned Vs Completed Ratio
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points planned during sprint planning.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points moved to PD.
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by V2 resources.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by LT resources.
Note on Y1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for V2 resources.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for LT resources.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for V2 resources.
Note on AB1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for LT resources.
Note on AC1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered by V2 resources - Total number of story points re-opened.
Note on AA10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tickets are in TESTING Bucket

## Marvel knights (hidden)
Week Starting On | Planned Story Points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Old Dates | Row Labels | Sum of V2 | Sum of LT | Row Labels | Sum of Rework | Sum of QA Passed
LCW: 5/4 - 5/11 |  | 17 | 15 | 2 | 0 | 0 | 0 | 0 | [5 empty] | 2020-05-04 | LCW: 6/29 - 7/06 | 11 | 0 | LCW: 6/29 - 7/06 | 0 | 11
LCW: 5/11 - 5/18 |  | 23 | 16 | 7 | 1 | 1 | 0 | 0 | [5 empty] | 2020-05-11 |  | 12 | 0 | LCW: 7/06 - 7/13 | 0 | 12
LCW: 5/18 - 5/25 |  | 18 | 9 | 7 | 1 | 0 | 0 | 0 | [5 empty] | 2020-05-18 | LCW: 7/13 - 7/20 | 10 | 0 | LCW: 7/13 - 7/20 | 0 | 10
LCW: 5/25 - 6/01 |  | 12 | 10 | 2 | 0 | 0 | 0 | 0 | [5 empty] | 2020-05-25 | LCW: 7/20 - 7/27 | 15 | 0 | LCW: 7/20 - 7/27 | 0 | 15
LCW: 6/01 - 6/08 |  | 20 | 18 | 2 | 0 | 1 | 0 | 0 | [5 empty] | 2020-06-01 | LCW: 7/27 - 8/03 | 11 | 0 | LCW: 7/27 - 8/03 | 0 | 11
LCW: 6/08 - 6/15 |  | 16 | 16 | 0 | 1 | 1 | 0 | 0 |  |  |  |  | 0% | 2020-06-08 | LCW: 8/03 - 8/10 | 8 | 0 | LCW: 8/03 - 8/10 | 0 | 8
LCW: 6/15 - 6/22 |  | 11 | 9 | 0 | 1 | 0 | 0 | 0 |  |  | 0% |  | 0% | 2020-06-15 | LCW: 8/10 - 8/17 | 13 | 0 | LCW: 8/10 - 8/17 | 0 | 13
LCW: 6/22 - 6/29 |  | 20 | 20 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | 0% | 2020-06-22 | LCW: 8/17 - 8/24 | 21 | 0 | LCW: 8/17 - 8/24 | 0 | 21
LCW: 6/29 - 7/06 |  | 11 | 11 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | 0% | 2020-06-29 | LCW: 8/24 - 8/31 | 10 | 3 | LCW: 8/24 - 8/31 | 5 | 5
LCW: 7/06 - 7/13 |  | 12 | 12 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | 0% | 2020-07-06 | LCW: 9/07 - 9/14 | 10 | 1 | LCW: 9/07 - 9/14 | 0 | 10
LCW: 7/13 - 7/20 |  | 10 | 10 | 0 | 0 | 3 | 0 | 0 |  |  | 0% |  | 0% | 2020-07-13 | LCW: 9/14 - 9/21 | 8 | 0 | LCW: 9/14 - 9/21 | 3 | 5
LCW: 7/20 - 7/27 |  | 15 | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | 0% | 2020-07-20 | LCW: 9/21 - 9/28 | 9 | 0 | LCW: 9/21 - 9/28 | 3 | 6
LCW: 7/27 - 8/03 |  | 11 | 11 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | 0% | 2020-07-27 | LCW: 9/28 - 10/05 | 9 | 0 | LCW: 9/28 - 10/05 | 0 | 9
LCW: 8/03 - 8/10 |  | 8 | 8 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | 0% | 2020-08-03 | LCW: 8/31 - 9/07 | 14 | 5 | LCW: 8/31 - 9/07 | 6 | 8
LCW: 8/10 - 8/17 |  | 13 | 13 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | 0% | 2020-08-10 | Grand Total | 161 | 9 | Grand Total | 17 | 144
LCW: 8/17 - 8/24 |  | 21 | 21 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | 0% | 2020-08-17
LCW: 8/24 - 8/31 |  | 13 | 10 | 3 | 5 | 0 | 0 | 0 | [5 empty] | 2020-08-24
LCW: 8/31 - 9/07 |  | 19 | 14 | 5 | 6 | 0 | 0 | 0 | [5 empty] | 2020-08-31 | Kanban Week | V2 | LT | QA Passed
LCW: 9/07 - 9/14 |  | 11 | 10 | 1 | 0 | 5 | 0 | 0 | [5 empty] | 2020-09-07 |  |  |  | Rework
LCW: 9/14 - 9/21 |  | 8 | 8 | 0 | 3 | 3 | 0 | 0 |  |  | 0% |  | 0% | 2020-09-14
LCW: 9/21 - 9/28 |  | 9 | 9 | 0 | 3 | 0 | 0 | 0 |  |  | 0% |  | 0% | 2020-09-21
LCW: 9/28 - 10/05 |  | 9 | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | 0% | 2020-09-28
[15 empty] | Row Labels | Sum of V2 Reopen Percentage | Sum of LT Reopen Percentage | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[15 empty] | LCW: 6/29 - 7/06 | 0 | 0 | LCW: 6/29 - 7/06 | 0 | 0
[15 empty] | LCW: 7/06 - 7/13 | 0 | 0 | LCW: 7/06 - 7/13 | 0 | 0
[15 empty] | LCW: 7/13 - 7/20 | 0 | 0 | LCW: 7/13 - 7/20 | 0 | 0
[15 empty] | LCW: 7/20 - 7/27 | 0 | 0 | LCW: 7/20 - 7/27 | 0 | 0
[15 empty] | LCW: 7/27 - 8/03 | 0 | 0 | LCW: 7/27 - 8/03 | 0 | 0
[15 empty] | LCW: 8/03 - 8/10 | 0 | 0 | LCW: 8/03 - 8/10 | 0 | 0
[15 empty] | LCW: 8/10 - 8/17 | 0 | 0 | LCW: 8/10 - 8/17 | 0 | 0
[15 empty] | LCW: 8/17 - 8/24 | 0 | 0 | LCW: 8/17 - 8/24 | 0 | 0
[15 empty] | LCW: 8/24 - 8/31 | 0.5 | 0 | LCW: 8/24 - 8/31 | 0 | 0
[15 empty] | LCW: 9/07 - 9/14 | 0 | 5 | LCW: 9/07 - 9/14 | 0 | 0
[15 empty] | LCW: 9/14 - 9/21 | 0.375 | 0 | LCW: 9/14 - 9/21 | 0 | 0
[15 empty] | LCW: 9/21 - 9/28 | 0.33333 | 0 | LCW: 9/21 - 9/28 | 0 | 0
[15 empty] | LCW: 9/28 - 10/05 | 0 | 0 | LCW: 9/28 - 10/05 | 0 | 0
[15 empty] | LCW: 8/31 - 9/07 | 0.42857 | 0 | LCW: 8/31 - 9/07 | 0 | 0
[15 empty] | Grand Total | 1.6369 | 5 | Grand Total | 0 | 0
[15 empty] | Sprint | V2 | LT | Sprint | V2 | LT

## CanopyNext
[8 empty] | Week Starting On | Planned Story points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio | Row Labels | Sum of V2 | Sum of LT |  | Row Labels | Sum of Rework | Sum of QA Passed | Row Labels | Sum of V2 Reopen Percentage | Sum of LT Reopen Percentage
PROJECT HEALTH DASHBOARD | [7 empty] | 2025 20: CAN 10/02 - 10/16 | 78 |  | 9 | 69 | 0 | 5 | 6 | 39 | [6 empty] | 2026 2: SLE 02/11 - 02/25 | 5 | 78 |  | 2026 2: SLE 02/11 - 02/25 | 0 | 5 | 2026 2: SLE 02/11 - 02/25 | 0% | 7.692% | Green
[8 empty] | 2025 21: CAN 10/16 - 10/30 | 76 |  | 12 | 64 | 0 | 10 | 9 | 45 | [6 empty] | 2026 3: SLE 02/25 - 03/11 | 12 | 61 |  | 2026 3: SLE 02/25 - 03/11 | 0 | 12 | 2026 3: SLE 02/25 - 03/11 | 0% | 8.197% | Red
[8 empty] | 2025 22: CAN 10/30 - 11/13 | 100 |  | 17 | 83 | 0 | 6 | 8 | 34 | [6 empty] | 2026 4: SLE 03/11 - 03/25 | 14 | 73 |  | 2026 4: SLE 03/11 - 03/25 | 0 | 14 | 2026 4: SLE 03/11 - 03/25 | 0% | 6.849% | Amber
[8 empty] | 2025 23: CAN 11/13 - 12/04 | 74 |  | 12 | 62 | 3 | 6 | 7 | 22 | [6 empty] | 2026 5: SLE 03/25 - 04/08 | 15 | 76 |  | 2026 5: SLE 03/25 - 04/08 | 4 | 11 | 2026 5: SLE 03/25 - 04/08 | 26.67% | 7.895%
| Project Name | LendingTree |  |  |  | Status Date | 2026-06-01 | 2025 24: CAN 12/04 - 12/18 | 92 |  | 8 | 84 | 2 | 18 | 3 | 15 | [6 empty] | 2026: SLE 04/08 - 04/30 | 13 | 58 |  | 2026: SLE 04/08 - 04/30 | 5 | 8 | 2026: SLE 04/08 - 04/30 | 38.46% | 31.03%
| Sub Project | SLE | [5 empty] | 2025 25 CAN 12/18 - 01/08 | 54 |  | 6 | 48 | 3 | 4 | 6 | 32 | [6 empty] | 2026: SLE 05/01 - 05/31 | 20 | 116 |  | 2026: SLE 05/01 - 05/31 | 13 | 7 | 2026: SLE 05/01 - 05/31 | 65% | 6.897%
| Delivery Manager | Rajesh |  |  |  | Overall Status | Green | 2026 1 CAN 01/08 - 1/22 | 66 |  | 7 | 59 | 3 | 11 | 6 | 11 | [10 empty] | Grand Total | 22 | 57 | Grand Total | 130.1% | 68.56%
| Project Manager/Lead | Puspendu Bhushan | [5 empty] | 2026 1 CAN 01/22 - 02/05 | 45 |  | 6 | 39 | 3 | 14 | 3 | 22
| Client POC | Sushanth Kancharla | [5 empty] | 2026 0: SLE 01/14 - 1/28 | 59 |  | 8 | 51 | 0 | 5 | 3 | 27
| Client Feedback | - | [5 empty] | 2026 1: SLE 01/28 - 02/11 | 88 |  | 8 | 80 | 0 | 0 | 5 | 38 | [6 empty] | Sprint | V2 | LT |  | QA Passed |  |  | Sprint | V2 | LT
| Team Allocation | [6 empty] | 2026 2: SLE 02/11 - 02/25 | 83 |  | 5 | 78 | 0 | 6 | 5 | 27 | [10 empty] | Rework
| Off-shore team | Allocated | 2 | Billable | 2 |  |  | 2026 3: SLE 02/25 - 03/11 | 73 |  | 12 | 61 | 0 | 5 | 7 | 28
| On-site team | Allocated | 6 |  |  |  |  | 2026 4: SLE 03/11 - 03/25 | 87 |  | 14 | 73 | 0 | 5 | 9 | 22
[8 empty] | 2026 5: SLE 03/25 - 04/08 | 91 |  | 15 | 76 | 4 | 6 | 11 | 28
[8 empty] | 2026: SLE 04/08 - 04/30 | 71 |  | 13 | 58 | 5 | 18 | 0 | 0
[8 empty] | 2026: SLE 05/01 - 05/31 | 137 |  | 20 | 117 | 13 | 8 | 0 | 0
[30 empty] | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[23 empty] | Row Labels | Sum of Planned Vs Completed ratio | [5 empty] | 2026 2: SLE 02/11 - 02/25 | 1 | 0.34615
[23 empty] | 2026 2: SLE 02/11 - 02/25 | 0.61446 | [5 empty] | 2026 3: SLE 02/25 - 03/11 | 0.58333 | 0.45902
[23 empty] | 2026 3: SLE 02/25 - 03/11 | 0.52055 | [5 empty] | 2026 4: SLE 03/11 - 03/25 | 0.64286 | 0.30137
[23 empty] | 2026 4: SLE 03/11 - 03/25 | 0.64368 | [5 empty] | 2026 5: SLE 03/25 - 04/08 | 0.73333 | 0.36842
[23 empty] | 2026 5: SLE 03/25 - 04/08 | 0.57143 | [5 empty] | 2026: SLE 04/08 - 04/30 | 0 | 0
[23 empty] | 2026: SLE 04/08 - 04/30 | 1 | [5 empty] | 2026: SLE 05/01 - 05/31 | 0 | 0
[23 empty] | 2026: SLE 05/01 - 05/31 | 1 | [5 empty] | Grand Total | 2.9595 | 1.475
[23 empty] | Grand Total | 4.3501
[30 empty] | Sprint | V2 | LT
[23 empty] | Sprint | Planned Vs Completed ratio
[25 empty] | Sprint | V2 | LT
[25 empty] | 2026 2: SLE 02/11 - 02/25 | 5 | 27
[25 empty] | 2026 3: SLE 02/25 - 03/11 | 7 | 28
[25 empty] | 2026 4: SLE 03/11 - 03/25 | 9 | 22
[25 empty] | 2026 5: SLE 03/25 - 04/08 | 11 | 28
[25 empty] | 2026: SLE 04/08 - 04/30 | 0 | 0
[25 empty] | 2026: SLE 05/01 - 05/31 | 0 | 0
[25 empty] | Sprint | V2 | LT
[25 empty] | 2026 2: SLE 02/11 - 02/25 | 0 | 6
[25 empty] | 2026 3: SLE 02/25 - 03/11 | 0 | 5
[25 empty] | 2026 4: SLE 03/11 - 03/25 | 0 | 5
[25 empty] | 2026 5: SLE 03/25 - 04/08 | 4 | 6
[25 empty] | 2026: SLE 04/08 - 04/30 | 5 | 18
[25 empty] | 2026: SLE 05/01 - 05/31 | 13 | 8
Note on R1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sprint name
Note on S1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points planned during sprint planning.
Note on T1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points moved to PD.
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by V2 resources.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by LT resources.
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for V2 resources.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for LT resources.
Note on Y1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for V2 resources.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for LT resources.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered by V2 resources - Total number of story points re-opened.
Note on AB1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by V2 resources Over Total number of story points re-opened.
Note on AC1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by LT resources over Total number of story points re-opened.
Note on AD1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by V2 resources over Total number of story points carry-over.
Note on AE1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ratio of Total number of story points delivered by LT resources over Total number of story points carry-over.
Note on I13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vishal is a shared resource for Canopy and Partner Central.

## UALS (InActive)
[8 empty] | Week Starting On | Planned Story Points | Actual Delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio | V2 InValid Reopen SP | Row Labels | Sum of V2 | Sum of LT |  | Row Labels | Sum of Rework | Sum of QA Passed
PROJECT HEALTH DASHBOARD | [7 empty] | UALS 2025 (12.1): 12/01-12/08 |  |  | 4 | 12 | 2 | 15 | 5 | 30 | [7 empty] | UALS 2026 (1.4): 1/20-1/26 | 0 | 14 |  | UALS 2026 (1.4): 1/20-1/26 | 0 | 0 | Green
[8 empty] | UALS 2025 (12.2): 12/08-12/15 |  |  | 0 | 0 | 0 | 0 | 5 | 46 | [7 empty] | UALS 2026 (1.5): 1/26-2/02 | 0 | 13 |  | UALS 2026 (1.5): 1/26-2/02 | 0 | 0 | Red
[8 empty] | UALS 2025 (12.3): 12/15-12/22 |  |  | 0 | 22 | 1 | 5 | 6 | 45 | [7 empty] | UALS 2026 (2.1): 2/02-2/09 | 1 | 17 |  | UALS 2026 (2.1): 2/02-2/09 | 0 | 1 | Amber
[8 empty] | UALS 2025 (12.4): 12/22-01/05 |  |  | 2 | 13 | 3 | 9 | 7 | 40 | [7 empty] | UALS 2026 (2.2): 2/09-2/23 | 5 | 23 |  | UALS 2026 (2.2): 2/09-2/23 | 0 | 5
| Project Name | LendingTree |  |  |  | Status Date | 2026-04-06 | UALS 2026 (1.2): 01/05-01/12 |  |  | 9 | 23 | 5 | 8 | 0 | 35 | [7 empty] | UALS 2026 (3.1): 2/23-3/09 | 4 | 40 |  | UALS 2026 (3.1): 2/23-3/09 | 4 | 0
| Sub Project | Unified Agent Led Shopping | [5 empty] | UALS 2026 (1.3): 01/12-01/19 |  |  | 2 | 10 | 2 | 11 | 0 | 36 | [7 empty] | UALS 2026 (3.2): 3/09-3/23 | 12 | 27 |  | UALS 2026 (3.2): 3/09-3/23 | 4 | 8
| Delivery Manager | Rajesh |  |  |  | Overall Status | Green | UALS 2026 (1.4): 1/20-1/26 |  |  | 0 | 14 | 0 | 13 | 5 | 38 | [7 empty] | Grand Total | 22 | 134 |  | Grand Total | 8 | 14
| Project Manager/Lead | Payal Butala | [5 empty] | UALS 2026 (1.5): 1/26-2/02 |  |  | 0 | 13 | 0 | 18 | 0 | 36
| Client POC | - | [5 empty] | UALS 2026 (2.1): 2/02-2/09 |  |  | 1 | 17 | 0 | 9 | 9 | 37
| Client Feedback | - | [5 empty] | UALS 2026 (2.2): 2/09-2/23 |  |  | 5 | 23 | 0 | 32 | 2 | 29 | [7 empty] | Sprint | V2 | LT |  | QA Passed
| Team Allocation | [6 empty] | UALS 2026 (3.1): 2/23-3/09 |  |  | 4 | 40 | 4 | 6 | 2 | 18 | [11 empty] | Rework
| Off-shore team | Allocated | 1 | Billable | 1 |  |  | UALS 2026 (3.2): 3/09-3/23 |  |  | 12 | 27 | 4 | 2 | 0 | 0
| On-site team | Allocated | 6 (4 Dev 1 QA, 1 Designer)
[24 empty] | Row Labels | Sum of V2 Reopen Percentage | Sum of LT Reopen Percentage |  | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[24 empty] | UALS 2026 (1.4): 1/20-1/26 | 0 | 0.92857 |  | UALS 2026 (1.4): 1/20-1/26 | 0 | 2.7143
[24 empty] | UALS 2026 (1.5): 1/26-2/02 | 0 | 1.3846 |  | UALS 2026 (1.5): 1/26-2/02 | 0 | 2.7692
[24 empty] | UALS 2026 (2.1): 2/02-2/09 | 0 | 0.52941 |  | UALS 2026 (2.1): 2/02-2/09 | 9 | 2.1765 | n
[24 empty] | UALS 2026 (2.2): 2/09-2/23 | 1 | 1.3913 |  | UALS 2026 (2.2): 2/09-2/23 | 0.4 | 1.2609
[24 empty] | UALS 2026 (3.1): 2/23-3/09 | 0.33333 | 0.15 |  | UALS 2026 (3.1): 2/23-3/09 | 0.5 | 0.45
[24 empty] | UALS 2026 (3.2): 3/09-3/23 | 0 | 0.074074 |  | UALS 2026 (3.2): 3/09-3/23 | 0 | 0
[24 empty] | Grand Total | 1.3333 | 4.458 |  | Grand Total | 9.9 | 9.3709
[24 empty] | Sprint | V2 | LT |  | Sprint | V2 | LT
[24 empty] | Row Labels | Sum of Planned Vs Completed ratio |  | Sprint | V2 | LT
[24 empty] | UALS 2026 (1.4): 1/20-1/26 | 0.24561 |  | UALS 2026 (1.4): 1/20-1/26 | 0 | 13
[24 empty] | UALS 2026 (1.5): 1/26-2/02 | 0.26531 |  | UALS 2026 (1.5): 1/26-2/02 | 0 | 18
[24 empty] | UALS 2026 (2.1): 2/02-2/09 | 0.28125 |  | UALS 2026 (2.1): 2/02-2/09 | 0 | 9
[24 empty] | UALS 2026 (2.2): 2/09-2/23 | 0.47458 |  | UALS 2026 (2.2): 2/09-2/23 | 0 | 32
[24 empty] | UALS 2026 (3.1): 2/23-3/09 | 0.6875 |  | UALS 2026 (3.1): 2/23-3/09 | 4 | 6
[24 empty] | UALS 2026 (3.2): 3/09-3/23 | 1 |  | UALS 2026 (3.2): 3/09-3/23 | 4 | 2
[24 empty] | Grand Total | 2.9542
[24 empty] | Sprint | Sum of Planned Vs Completed Ratio |  | Sprint | V2 | LT
[27 empty] | UALS 2026 (1.4): 1/20-1/26 | 5 | 38
[27 empty] | UALS 2026 (1.5): 1/26-2/02 | 0 | 36
[27 empty] | UALS 2026 (2.1): 2/02-2/09 | 9 | 37
[27 empty] | UALS 2026 (2.2): 2/09-2/23 | 2 | 29
[27 empty] | UALS 2026 (3.1): 2/23-3/09 | 2 | 18
[27 empty] | UALS 2026 (3.2): 3/09-3/23 | 0 | 0
Note on S1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points planned during sprint planning.
Note on T1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points moved to PD.
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by V2 resources.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered (moved to PD) by LT resources.
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for V2 resources.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points re-opened by external QA for LT resources.
Note on Y1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for V2 resources.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points carry over during the sprint for LT resources.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total number of story points delivered by V2 resources - Total number of story points re-opened.

## Wordpress Modernization (InActi
[8 empty] | Week Starting On | Planned story points | Actual delivered | V2 | LT | Rework | Reopened SP (LT) | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio
[8 empty] | WPML 07/01 - 07/31 | 42 | 42 | 25 | 17 | 3 | 1 | 0 | 0 | 22 | [5 empty] | Row Labels | Sum of V2 | Sum of LT | Row Labels | Sum of Rework | Sum of QA Passed |  | Green
PROJECT HEALTH DASHBOARD | [7 empty] | WPML 08/01 - 08/31 | 52 | 52 | 11 | 41 | 3 | 3 | 0 | 0 | 8 | [5 empty] | WPML 09/01 - 09/30 | 19 | 68 | WPML 09/01 - 09/30 | 2 | 17 |  | Red
[8 empty] | WPML 09/01 - 09/30 | 87 | 87 | 19 | 68 | 2 | 10 | 0 | 0 | 17 | [5 empty] | WPML 10/01 -10/31 | 17 | 70 | WPML 10/01 -10/31 | 2 | 15 |  | Amber
[8 empty] | WPML 10/01 -10/31 | 87 | 87 | 17 | 70 | 2 | 6 | 0 | 0 | 15 | [5 empty] | WPML 11/01 - 11/30 | 16 | 45 | WPML 11/01 - 11/30 | 0 | 16
[8 empty] | WPML 11/01 - 11/30 | 61 | 61 | 16 | 45 | 0 | 3 | 0 | 0 | 16 | [5 empty] | WPML 12/01 - 12/31 | 23 | 42 | WPML 12/01 - 12/31 | 3 | 20
| Project Name | LendingTree |  |  |  | Status Date | 2026-03-07 | WPML 12/01 - 12/31 | 65 | 65 | 23 | 42 | 3 | 5 | 0 | 0 | 20 | [5 empty] | WPML 01/01 - 01/31 | 8 | 60 | WPML 01/01 - 01/31 | 0 | 8
| Sub Project | Consumer Web | [5 empty] | WPML 01/01 - 01/31 | 68 | 68 | 8 | 60 | 0 | 11 | 0 | 0 | 8 | [5 empty] | WPML 02/01 - 02/28 | 19 | 56 | WPML 02/01 - 02/28 | 0 | 19
| Delivery Manager | Rajesh |  |  |  | Overall Status | Green | WPML 02/01 - 02/28 | 75 | 75 | 19 | 56 | 0 | 11 | 0 | 0 | 19 | [5 empty] | Grand Total | 102 | 341 | Grand Total | 7 | 95
| Project Manager/Lead | Daya
Client POC
| Client Feedback | - | [20 empty] | Sprint | V2 | LT
| Team Allocation | [22 empty] | 19 | 68
| Off-shore team | Allocated | 1 | Billable | 1 | [18 empty] | 17 | 70
| On-site team | Allocated | 4 | [20 empty] | 16 | 45 | QA Passed
[24 empty] | 23 | 42 | Rework
[24 empty] | 8 | 60
[24 empty] | 19 | 56
[23 empty] | Row Labels | Sum of LT Reopen Percentage | Sum of V2 Reopen Percentage |  | Row Labels | Sum of V2 Carryover Percentage | Sum of LT Carryover Percentage
[23 empty] | WPML 09/01 - 09/30 | 0.14706 | 0.10526 |  | WPML 09/01 - 09/30 | 0 | 0
[23 empty] | WPML 10/01 -10/31 | 0.085714 | 0.11765 |  | WPML 10/01 -10/31 | 0 | 0
[23 empty] | WPML 11/01 - 11/30 | 0.066667 | 0 |  | WPML 11/01 - 11/30 | 0 | 0
[23 empty] | WPML 12/01 - 12/31 | 0.11905 | 0.13043 |  | WPML 12/01 - 12/31 | 0 | 0
[23 empty] | WPML 01/01 - 01/31 | 0.18333 | 0 |  | WPML 01/01 - 01/31 | 0 | 0
[23 empty] | WPML 02/01 - 02/28 | 0.19643 | 0 |  | WPML 02/01 - 02/28 | 0 | 0
[23 empty] | Grand Total | 0.79825 | 0.35334 |  | Grand Total | 0 | 0
[23 empty] | Sprint | V2 | LT | Sprint | V2 | LT
[26 empty] | Row Labels | Sum of Planned Vs Completed ratio
[26 empty] | WPML 09/01 - 09/30 | 1
[26 empty] | WPML 10/01 -10/31 | 1
[23 empty] | Sprint | V2 | LT | WPML 11/01 - 11/30 | 1
[23 empty] | WPML 09/01 - 09/30 | 19 | 68 | WPML 12/01 - 12/31 | 1
[23 empty] | WPML 10/01 -10/31 | 17 | 70 | WPML 01/01 - 01/31 | 1
[23 empty] | WPML 11/01 - 11/30 | 16 | 45 | WPML 02/01 - 02/28 | 1
[23 empty] | WPML 12/01 - 12/31 | 23 | 42 | Grand Total | 6
[23 empty] | WPML 01/01 - 01/31 | 8 | 60
[23 empty] | WPML 02/01 - 02/28 | 19 | 56
[26 empty] | Sprint | Planned Vs Completed ratio
[23 empty] | Sprint | V2 | LT
[23 empty] | WPML 09/01 - 09/30 | 2 | 10
[23 empty] | WPML 10/01 -10/31 | 2 | 6
[23 empty] | WPML 11/01 - 11/30 | 0 | 3
[23 empty] | WPML 12/01 - 12/31 | 3 | 5
[23 empty] | WPML 01/01 - 01/31 | 0 | 11
[23 empty] | WPML 02/01 - 02/28 | 0 | 11
Note on T1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered by V2.
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Delivered by LT.
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story points re-opened by external QA for V2 resources.
Note on X1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story Points Reopen by LT.
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Story Points Carryover by LT.
Note on AA1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total QA Passed by V2
Note on U40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Less tickets because the team is transitioning from the WPM to the WPML board, and the Scrum team has instructed not to start any new tickets during this period.
Note on U41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3 Dev from V2 and 1 from LT side