## Slide 1: FLEX
March Report

## Slide 2: Agenda
Review of last month
  List of goals achieved in each sprint
  Key takeaways other than goals
Current State
  Challenges and Mitigation plans
Road Ahead
  Product Roadmap (next month, next quarter, long term)
  Resource requirements
  Skill upgrades

## Slide 3: Goals Achieved in March
  FLEX-792: Redesign the SMB Offers page to show Real offers, instead of static data.
    Status: Completed
  Flex-739: Home Portfolio Leads: Implement Home Portfolio Leads with Offer Rate table.
    Status: In Progress (96%)
  Flex-784: Funnels - Cross Sell Variations
    Status: In Progress (81%)
  FLEX-584: Verify User’s Phone number using a Third Party API for BL and HE
    Status: In Progress (94%)
  FLEX-911: Remove phone number and email from the PL page
    Status: In Progress (60%)

## Slide 4: Carryover and Reopen Details
    Flex '26 Sprint 4: 2/19 - 3/5
      Flex-838,Flex-839,Flex-840 belonging to Epic FLEX-784 (Funnels Cross sell variation) carried over as there were some design elements in Figma which were initially thought to be not in scope.
    Flex '26 Sprint 5: 3/5 - 3/19
      No Carryover

## Slide 5: Key Achievements
  FLEX-784: Funnels Cross Sell variations.
  Flex-584: Identity Verification in BL & HE is very close to completion.

## Slide 6: Challenges Faced and Mitigation plan
QA Bandwidth is low as 6 Developers outnumber 2 QA

## Slide 7: Project RoadMap
Identity Verification in BL & HE
Ping/Post Marketing Bid API – Phase 1 (Personal Loans)
Funnels Cross Sell Variations
Form Enrichment - Credit Bureau File - LTIS-557

## Slide 8: Resources and Skills
Resources Requirement – No
Skills – No